## TỔNG
Tổng hợp đề
STT | Thể loại | Course | Trạng thái | Các kỳ xuất hiện (Nếu đã ra) | Trạng thái | Buổi | Nội dung đề
1 | Coursera | Course 1: Initiating and Planing Projects | Đã từng ra | 1. SP24 2. FA24 - RE | Đã dạy | Buổi 3 | Consider three projects that you either currently work on or have worked on in the past. Based on your understanding of project organizations, decide what type of organization you think those projects are using and also what type of organization you think those projects should or should have used. Conversely look at projects going on around you – you can find them in the news and see if you can identify what types of project organizations they use, do you agree with these choices?
2 | Coursera | Course 1: Initiating and Planing Projects | Đã từng ra | 1. SP24 - RE 2. FA24 3. SP25 | Đã dạy | Buổi 3 | Look at one project that you are involved with, have been involved with OR look at a project going on around you (again the news and current events can supply examples). For the project you select, identify 3 stakeholders and decide if they are: High power or low power High interest or low interest Are they unaware of the project? Are they resistant to the project? Are they neutral? Are they supportive? Are they leading? Based on your findings, design your strategy for how you would manage these stakeholders.
3 | Coursera | Course 1: Initiating and Planing Projects | Chưa từng ra |  | Đã dạy |  | Referencing the project you have been using in our previous exercises, identify common sources of conflict within the project environment and how authority and influence have been used both in positive and negative ways.
4 | Coursera | Course 2: Budgeting and Scheduling Projects | Đã từng ra | 1. SU24 - RE | Đã dạy | Buổi 3 | Create a Responsibility Assignment Matrix for RAM for a project that you are currently working on, have worked on in the past or a project that you have been following. Of course to do this, you need to create some work packages or activities which can be assigned to the team and you need to come up with team members who will complete this work. You do not have to create a RAM for the entire duration of the project, try to include at least five to ten activities.
5 | Coursera | Course 2: Budgeting and Scheduling Projects | Chưa từng ra |  | Đã dạy |  | Look at the activities you have included in the RAM you created for Module 2 of this course. For each activity, decide how you think the estimates should be created (parametric, analogous or another technique we discussed in our lesson) and who should be doing the estimating.
6 | Coursera | Course 2: Budgeting and Scheduling Projects | Đã từng ra | 1. SU24 | Đã dạy | Buổi 3 | Look at the activities you estimated and determine what their relationships would be if you were to use them to create a schedule. Decide which activity should occur first, what happens next, can any of the work occur in parallel? And for each consider what the relationship should be between them, is it finish-start, finish-finish, start-start?
7 | Coursera | Course 3: Managing Project Risks and Changes | Đã từng ra | 1. SP24 - RE 2. FA24 | Đã dạy | Buổi 3 | Go back to the three stakeholders you identified during our activity for the second module of our first course. Create a communication plan that includes each of these stakeholders and the communications you believe they should receive.
8 | Coursera | Course 3: Managing Project Risks and Changes | Đã từng ra | 1. SP24 2. FA24 - RE 3. SP25 | Đã dạy | Buổi 3 | For the project that you have been using in our previous activities, identify at least three significant risks that you think the project faces. For each risk determine how likely you think it is to occur (the probability) and the impact if it does occur. Create your own scoring system for probability and impact. You might use High-Medium-Low; you might use numeric values or you might use percentages. Define a response for each of these risks.
9 | Coursera | Course 3: Managing Project Risks and Changes | Chưa từng ra |  | Đã dạy |  | For the project that you have been using in our previous activities, document three to five changes that you think could really occur or be requested.
10 (*) | Đề mới/Foundation | FPT | Đã từng ra | 1. SP24 2. SP24 - RE 3. SU24 4. SU24 - RE 5. FA24 6. FA24 - RE 7. SP25 | Đã dạy | Buổi 2 | Give detailed descriptions for the project in which you mention clearly its key characteristics: project title, project purpose/objectives (unique), project timeframe (temporary), customer/sponsor (clearly defined), project milestones (time constraints), and other project constraints (cost, resources), Success criteria, Project Deliverables, In-Scope Items, Out-Scope Items.
11 | Đề mới/Foundation | FPT | Đã từng ra | 1. SU24 | Đã dạy | Buổi 2 | Define at least 5 roles you might have in your project team and at least 2 responsibilities (mapped to the project work packages and/or activities) for each role.
12 | Đề mới/Foundation | FPT | Đã từng ra | 1. SU24 2. SP25 | Đã dạy | Buổi 2 | Identify at least 10 items that you believe either are or should be out of scope for the project. Provide classification (in-scope or out-of-scope) and detailed description for each item.
13 | Đề mới/Foundation | FPT | Đã từng ra | 1. SU24 2. SU24 - RE | Đã dạy | Buổi 2 | Provide at least 5 quality cost items (prevention, appraisal, or external failure costs), description, and estimation for each cost item. The estimation should be an effort (man-days, man-hours) for labor costs.
14 | Đề mới/Foundation | FPT | Đã từng ra | 1. SU24 - RE | Đã dạy | Buổi 2 | Defines at least 5 quality assurance (QA) or quality control (QC) activities for the project. For each activity, you need to classify it to QA or QC + clearly describe the purpose, when, and how to do it.
15 | Đề mới/Foundation | FPT | Đã từng ra | 1. SU24 - RE | Đã dạy | Buổi 2 | Identify at least 4 project phases/iterations and 2 main deliverables in each phase/iteration. You need to provide the description for each of the identified deliverables about its content/purpose.
16
17
18
19
20
21
22
23
24
25
26