## Lý thuyết
CRITICAL PATH
Activity # | Activity |  | Duration | Predecess |  | Duration
1 | Hiring Workers |  | 20 | - |  |  |  | ES | Early Start
2 | Buying Supplies |  | 10 | - | ES | Activity # | EF | EF | Early Finish
3 | Building Stage |  | 20 | 1,2 | Float |  |  | LS | Late Start
4 | Installing Lights |  | 5 | 3 | LS | Duration | LF | LF | Late Finish
5 | Installing Sound |  | 10 | 3
6 | Installing Seats |  | 7 | 3
7 | Cleaing Stage |  | 2 | 4,5,6
Forward Pass – For Early Start and Early Finish ES for first activity or activities is 1 EF = (ES + Duration) – 1 ES for successor activity = EF of predecessor + 1 What if an activity has more than one predecessor? Use the HIGHEST EF |  |  |  |  | Backward Pass – For Late Start and Late Finish LF of last activity = latest EF – We finish the project on one day and one day only! LS = (LF – Duration) + 1 LF for predecessor activity = (LS – 1) What if an activity has more than one successor? Use the LOWEST LS
Float Late Start – Early Start OR Late Finish – Early Finish (Both will give you the same answer if you have completed your network correctly.)
[8 empty] | 41 | Activity 4 | 45
|  | 1 | Activity 1 | 20 |  |  |  | 5
|  | 0 | [5 empty] | 46 | 5 | 50
|  | 1 | 20 | 20
Start |  |  |  |  | 21 | Activity 3 | 40 | 41 | Activity 5 | 50 | 51 | Activity 7 | 52 | Finish
[5 empty] | 0 |  |  | 0 |  |  | 0
[5 empty] | 21 | 20 | 40 | 41 | 10 | 50 | 51 | 2 | 52
|  | 1 | Activity 2 | 10
|  | 10 | [5 empty] | 41 | Activity 6 | 47
|  | 11 | 10 | 20 |  |  |  | 3
[8 empty] | 44 | 7 | 50

## Sheet3
Start