## Xác định mối quan hệ giữa các hoạt động (Activity Dependencies)

### A. LÝ THUYẾT

### I. Khái niệm chính

Khi lập lịch dự án, ta cần xác định mối quan hệ (dependencies) giữa các hoạt động (activities). Mỗi hoạt động sẽ có:

- Thứ tự thực hiện

- Có thể thực hiện song song (parallel) hay không

- Kiểu quan hệ (relationship type)

### II. Các kiểu mối quan hệ phổ biến (Activity Relationship Types)

| Tên gọi | Ký hiệu | Ý nghĩa |
| --- | --- | --- |
| Finish-to-Start | FS | Hoạt động sau bắt đầu sau khi hoạt động trước kết thúc (phổ biến nhất) |
| Start-to-Start | SS | Hai hoạt động bắt đầu cùng lúc hoặc sau nhau |
| Finish-to-Finish | FF | Hai hoạt động kết thúc cùng lúc hoặc sau nhau |
| Start-to-Finish | SF | Hiếm – Hoạt động sau kết thúc sau khi hoạt động trước bắt đầu |

Ví dụ:

- FS:

  - Xây móng → Xây tường -> Trát tường -> Sơn

  - Viết nội dung → Thiết kế bản trình bày

- SS:

  - Lập kế hoạch sự kiện ↔ Đặt dịch vụ ăn uống

  - Viết bài báo ↔ Tìm hình ảnh minh họa

  - Thiết kế slide <-> Tìm hình ảnh minh họa

- FF:

  - Duyệt lại slide ↔ Luyện tập thuyết trình

  - Kiểm tra sản phẩm ↔ Cập nhật báo cáo chất lượng

- SF:

  - Trực ca đêm kết thúc khi ca sáng bắt đầu

  - Tắt dịch vụ cũ khi dịch vụ mới bắt đầu hoạt động

### B. BÀI GIẢI

| Predecessor Activity | Successor Activity | Relationship Type | Can it be parallel? | Reasoning |
| --- | --- | --- | --- | --- |
| 1. Requirements gathering | 2. Wireframe design | Finish-to-Start (FS) | No | Wireframes depend on confirmed requirements |
| 2. Wireframe design | 3. UI development | Finish-to-Start (FS) | No | UI coding follows design approval |
| 3. UI development | 6. Frontend-backend integration | Finish-to-Start (FS) | No | Integration begins after the frontend is ready |
| 4. Backend API setup | 6. Frontend-backend integration | Finish-to-Start (FS) | No | Integration also requires backend readiness |
| 5. Database schema design | 4. Backend API setup | Finish-to-Start (FS) | No | Backend depends on the DB structure |
| 6. Integration | 7. Testing & bug fixing | Finish-to-Start (FS) | No | Testing starts after full integration |
| 7. Testing | 8. Client demo preparation | Finish-to-Start (FS) | No | Demo happens after the stable version |
| 7. Testing | 10. Post-deployment support | Finish-to-Finish (FF) | Partial | Testing and deployment support end together |
| 8. Demo preparation | 9. Deployment to the internal server | Finish-to-Start (FS) | No | Demo approval leads to deployment |