PMG201c - Practical Exam 1 (Fall 2025)

You have developed a unique, niche consumer product, and your project is to validate its market viability through a temporary pop-up retail operation. The project requires securing permits, designing and building the display, managing inventory, training student sales staff, and achieving a sales goal of $15,000 in gross revenue. The pop-up operation must run for two consecutive weeks. The setup and operational costs (excluding product manufacturing cost) are strictly limited to $1500, and the budget constraint demands that the total inventory shrinkage/loss be kept below 2% of the total inventory value. For quality, the customer satisfaction rating, measured by post-purchase surveys, must exceed 90% positive feedback regarding product quality and the retail experience.

Request 1 (20%): develop a narrative charter statement that includes the following details

1. Project name,

2. Justifications (purpose & reasons to implement this project),

3. Project constraints, in terms of scope, time, cost/budget, and quality.

Request 2 (20%): provide at least five main cost/budget items. Each cost/budget item, you need to provide following details: name, description, estimation along with the way to estimate (how to estimate, person in charged,..)

Request 3 (30%): develop communication plan for the project where you:

1. Define at three project stakeholders (project-internal, organization-internal, external)

2. Create a communication plan for each of those stakeholders and the communications you believe they should receive. Each communication needs to include following details: information, purpose, frequency, method or format, responsible.

Request 4 (30%): identify three project risks by listing out the risk title/name, description, possible impacts (in term of scope or quality, time, and cost), and relevant risk response plans (mitigation, contingency).

Request 1

1. Project Name

Niche Consumer Product Market Validation via Pop-up Retail

2. Project Justifications (Purpose & Reasons)

The purpose of this project is to validate the market viability of a unique, niche consumer product through a real-world selling environment.

Instead of relying solely on surveys or online testing, the project uses a temporary pop-up retail operation to directly observe customer behavior, purchasing decisions, and satisfaction.

This project is implemented to:

Test real customer demand and willingness to pay for the product.

- Collect direct feedback on product quality and retail experience.

- Evaluate operational feasibility, including inventory management and sales staff performance.

- Reduce long-term business risk before committing to large-scale production or permanent retail investment.

3. Project Constraints

a. Scope Constraints

- The project scope is limited to planning, setting up, and operating one temporary pop-up retail store.

- Included activities: securing permits, designing and building the product display, managing inventory, training student sales staff, conducting sales, and collecting customer feedback.

- Excluded from scope: product manufacturing, long-term retail operations, online sales platforms, and post-project marketing campaigns beyond feedback analysis.

b. Time Constraints

- The pop-up retail operation must run for two consecutive weeks only.

- All preparation activities, including permits, display setup, and staff training, must be completed before the opening date.

- The project must conclude immediately after the two-week operation and post-sale evaluation.

c. Cost / Budget Constraints

- Total setup and operational costs (excluding product manufacturing costs) are strictly capped at USD 1,500.

- All expenses related to permits, display materials, staffing support, and operations must remain within this fixed budget.

- No budget overrun is allowed.

d. Quality Constraints

- Inventory shrinkage or loss must be kept below 2% of total inventory value.

- Customer satisfaction, measured through post-purchase surveys, must achieve more than 90% positive feedback related to product quality and retail experience.

- Sales staff must be adequately trained to ensure consistent service quality throughout the operation.

Request 2

The project budget focuses on controlling setup and operational costs while ensuring efficient execution during the two-week pop-up retail operation.

1. Permit & Licensing Cost

Description: This cost covers the fees required to obtain temporary retail permits from local authorities, allowing the pop-up store to operate legally.

Estimated Cost: USD 200

Person in Charge: Project Manager

2. Display & Booth Setup Cost

Description: This cost includes designing, constructing, and decorating the pop-up booth, such as tables, shelves, banners, lighting, signage, and basic visual materials.

Estimated Cost: USD 400

Person in Charge: Project Manager in coordination with the Design and Operations Lead

3. Inventory Handling & Storage Cost

Description: This cost covers inventory storage materials, security locks, tagging systems, and loss-prevention tools required to ensure inventory shrinkage remains below 2%.

Estimated Cost: USD 300

Person in Charge: Inventory Manager under the supervision of the Project Manager

4. Sales Staff Training Cost

Description: This cost relates to training student sales staff, including training materials, printed manuals, and rehearsal sessions prior to store opening to ensure consistent service quality.

Estimated Cost: USD 200

Person in Charge: Project Manager and Sales Team Lead

5. Operational & Daily Running Costs

Description: This category includes daily operational expenses such as utilities, cleaning supplies, minor maintenance items, and transaction-related costs during the two-week operation.

Estimated Cost: USD 300

Person in Charge: Operations Coordinator reporting to the Project Manager

Request 3

1. Project Stakeholders

- Project-internal stakeholder: Project Team (Project Manager, Inventory Staff, Sales Staff, Setup Team)

- Organization-internal stakeholder: Project Sponsor / Business Owner

- External stakeholder: Customers (Pop-up Store Visitors)

2. Communication Plans

A. Project Team

- Information: Project schedule, task assignments, inventory status, daily sales targets

- Purpose: Ensure clear responsibilities, smooth coordination, and progress monitoring

- Frequency: Weekly during preparation; daily during the pop-up operation

- Method / Format: Face-to-face meetings, messaging groups, task boards

- Responsible: Project Manager

B. Project Sponsor / Business Owner

- Information: Project progress, budget usage, revenue performance, key risks

- Purpose: Report project status and obtain approval for major decisions or changes

- Frequency: Weekly reports and final summary after the two-week operation

- Method / Format: Email reports and brief meetings

- Responsible: Project Manager

C. Customers

- Information: Product features, pricing, promotions, post-purchase satisfaction surveys

- Purpose: Encourage purchases and collect feedback on product quality and retail experience

- Frequency: Throughout the pop-up operation

- Method / Format: In-store communication and QR-based surveys

- Responsible: Sales Staff and Project Manager

Request 4

Risk 1: Low Sales Performance

Risk Description:
Sales revenue falls below the USD 15,000 target due to low customer traffic or insufficient product attractiveness.

Possible Impacts:

- Scope / Quality: Failure to validate market feasibility

- Time: Inability to recover lost sales due to the fixed two-week pop-up duration

- Cost: Operational expenses cannot be recovered through sales revenue

Probability: Medium (3)
Impact: High (4)
Risk Score: 3 × 4 = 12 (High)

Mitigation Plan:

- Select a high-traffic pop-up retail location

- Train sales staff in product knowledge and consultative selling techniques

- Introduce promotional campaigns and bundled product offers

Contingency Plan:

- Apply short-term price discounts if sales performance remains low

- Intensify selling activities during peak customer hours

- Focus sales efforts on best-selling products

Risk 2: Inventory Loss / Shrinkage Exceeding 2%

Risk Description:
Inventory loss caused by theft, damage, or mishandling results in shrinkage exceeding the permitted 2% limit.

Possible Impacts:

- Scope / Quality: Inventory control and quality requirements are not met

- Time: Additional time required for inventory reconciliation and investigation

- Cost: Increased operational costs and reduced profitability

Probability: Medium (3)
Impact: High (4)
Risk Score: 3 × 4 = 12 (High)

Mitigation Plan:

- Perform daily inventory counts and reconciliation

- Clearly assign inventory management responsibilities

- Restrict physical access to storage and inventory areas

Contingency Plan:

- Temporarily suspend the sale of high-risk inventory items

- Adjust pricing strategies to partially offset inventory losses

- Increase monitoring and supervision at sales counters

Risk 3: Low Customer Satisfaction Rating

Risk Description:
Customer dissatisfaction with product quality or the retail experience leads to positive feedback falling below the 90% threshold.

Possible Impacts:

- Scope / Quality: Project quality objectives are not achieved

- Time: Additional effort and time required to resolve customer complaints

- Cost: Extra costs associated with refunds, exchanges, or customer incentives

Probability: Low to Medium (2)
Impact: Major (4)
Risk Score: 2 × 4 = 8 (Medium)

Mitigation Plan:

- Provide customer service training to all sales staff

- Conduct quality inspections on products prior to sale

- Design a clear, intuitive, and customer-friendly store layout

Contingency Plan:

- Resolve customer complaints immediately at the point of sale

- Offer product exchanges, refunds, or goodwill incentives

- Adjust sales and service processes based on customer feedback