1. True or False: The Project Sponsor is responsible for stakeholder expectations management

A. False

B. True

Project Sponsor cung cấp tài chính và quyền hạn, nhưng người chịu trách nhiệm chính trong việc quản lý kỳ vọng của các bên liên quan (Stakeholder expectations management) là Project Manager (PM). PM là người trực tiếp giao tiếp và xử lý hàng ngày.

2. Which one of there is current view of conflict? Quan điểm hiện đại cho rằng xung đột là tất yếu và có thể quản lý để tốt hơn

A. Caused by troublemakers

B. Always bad

C. Should be avoided

D. Can ( and should) be managed

3. True or False: When you choose to transfer your project risk to a third party, it may give rise to secondary risk that did not exist prior to the transfer -> ví dụ có thể gặp rủi ro nhà thầu phá sản

A. True

B. False

4. True or False: The critical path is the longest path ( the biggest total duration path) through the network and represents the shortest duration in which all the activities of the project can be completed.

A. False

B. True

5. A project management plan should be realistic in order to be used to manage the project. which of the following is the best method to archive a realistic project management plan?

A. The sponsor creates the project management plan based on input from the project manager

B. The functional manager creates the project management plan based on input from the project manager

C. The project manager creates the project management plan based on input from senior management

D. The project manager creates the project management plan based on input from the team

6. Who might not be your project's stakeholders?

A. Project team members

B. Project management learn

C. Customer/User

D. Performing organizations

E. Sponsor

F. People that are not impacted by your project

7. When you use the RACI or responsible, Accountable, Consult, Inform version of the RAM, those Accountable persons are:

A. Providing subject matter expertise

B. Making the final decision

C. Being kept updated about project progress

D. Completing the work

8. All of the following are inputs to estimating activity duration except: là đầu ra ko phải ước tính

A. Enterprise Environmental Factor & Organizational Process Assets

B. Risk Register & Scope Statement

C. Project Documents Updates & Requirements Specifications

D. Resource Calendars & Resource Breakdown Structure

9. True or False: You should compare your project performance against the performance measurement baseline to look for potential changes in the project.

A. True

B. False

10. True or False: Product quality focuses on the goods and services

A. False

B. True

11. True or False: A project manager spends 65% of his or her time communicating

A. False 90%

B. True

12. Which of the following is NOT the advantages of top-down estimating?

A. Quick

B. Activities do not need to be identified

C. Less costly to create

D. More Accurate

13. True or False: Performing quality control within the context of a project involves taking actions to eliminate causes of unsatisfactory project performance -> nguyên nhân gốc rễ là QA

A. False

B. True

14. You just came from a meeting with one of your project stakeholders, he knew well about your project and also it potential impacts, and actively engaged in ensuring that the project is a success. How would you classify him? ->  leading: đảm bảo thành công

A. Supportive

B. Neutral

C. Unaware

D. Leading

15. True or False: Project Human Resource Management includes the processes that organize, manage, and lead the project team -> tổ chức quản lý lãnh đạo nhóm dự án

A. False

B. True

16. The three components of the triple constraint are : Tam giác ràng buộc

A. Scope, Cost, Time

B. Scope, Quality, Cost

C. Scope, Performance, Cost

D. Scope, Performance, time

17. True or False: A project is defined as being unique and temporary, with an undefined start and finish > phải có thời gian cụ thể

A. True

B. False

18. When you have good historical information which can be used in a reliable formula or model, you will probably use -> khi có dữ liệu đáng tin cậy ta dùng ước tính tham số

A. Parametric estimating

B. Extract estimating

C. Analogous estimating

D. Bottoms up estimating

19. In a project context, risk is defined as -> có thể vừa tích cực vừa tiêu cực

A. The probability of an event having a positive or negative effect on at least one project objective

B. The impact of not completing the project on time and within budget

C. An uncertain event that, if it occurs , will have a positive or negative effect on at least one project objective

D. An uncertain event that, if it occurs , will have a negative effect on at least one project objective.

20. The discipline of quality management complements the discipline of project management. Both recognize all but one of following -> không có company satisfaction

A. Company satisfaction

B. Prevention over inspection

C. Continuous improvement

D. Management Responsibility

21. If the response you choose is to exploit a risk this means that ->. Khai thác là làm cho rủi ro đó xảy ra

A. You actively do not consider the risk but establish contingency plan

B. You add steps to your plans make certain the opportunity is captured

C. You change your plan so that another party will be responsible for a partial amount of ownership of the opportunity

D. You create your plan to increase the probability and/or the impact of opportunity

22. True or False: if "develop online modules" needs to finish before "review online modules" can finish, that is called a finish to finish relationship -> FF

A. True

B. False

23. A useful tool in identifying risk is the SWOT analysis. What does SWOT stand for?

A . Strengths, Obstacles, weaknesses, and threats

B. Strengths, opportunities, winners, and threats

C. Scope, opportunities, weaknesses, and time

D. Strengths, opportunities, weaknesses, and threats

24. A project manager can defend against scope creep with a good _________-> chống trượt phạm vi bằng cách mọi thứ phải đi qua quy trình kiểm duyệt chính thức

A. Procurement process

B. Change control process

C. Risk management plan

D. Project management plan

25. True or False: Performing quality assurance within the context of a project involves taking actions to eliminate causes of unsatisfactory project performance -> QA là xoá bỏ nguyên nhân gốc rễ

A. False

B. True

26. True or False: The WBS should completely depict the scope of your project that if something is not in the WBS it is because it is NOT part of the project -> nếu ko nằm trong cấu trúc phân chia công việc thì không phải việc của mình

A. False

B. True

27.To calculate early finish(EF) of an activity, you will ->  EF = Early Start (ES) + Duration (Thời lượng)

A. Take its early start plus its estimated duration

B. Take its late start plus its estimated duration

C. Take its finish minus it estimated duration

D. Take its late finish

28. Should the Project Scope Statement document include? -> có tiêu chí nghiệm thu

A. Acceptance criteria

B. Milestones

C. WBS

D. WBS dictionary

29. True or False : Using bottom-up estimating techniques when the detail is available and the accuracy is needed -> có thông tin chi tiết là oke, chính xác

A. True

B. False

30. True or False: The crashing is the approach to add more resources into the activities to reduce their durations -> Làm gấp là thêm nguồn lực vào

A True

B False

31. Which one is not the different between assumptions and constraints?

A. Assumptions are believed to be true, while constraints are true in nature

B. Constraints are believed to be true, while assumptions are true in nature -> ngược rồi nên sai

C. Assumptions are good for project, while constraints are not good, most of time.

D. If assumptions become false, it is bad news for the project. however, if constraints are false, it is good

32. True or False: The Cost Baseline is equal to the total of Activity Cost Estimates plus contingency reserves ->  Cost Baseline = Chi phí các hoạt động + Contingency reserves (Dự phòng cho rủi ro đã biết)

A True

B False

33. A Project manager is trying to complete a software development project, but cannot enough attention for the project. Resources are focused on completing process-related work, and the project manager has little authority to assign resources. What form of organization must the project manager be working in? -> PM có ít quyền hạn thì làm Funtional

A. Functional

B. Matrix

C. Projectized

D. Coordinator

34. Which one is the correct matching of communication methods and explanations?

communications methods"

(1) interactive: tương tác hai chiều -> a

(2) Push: đẩy, gửi mail nhưng chưa chắc người nhận đã hiểu -> b

(3) pull: tự truy cập vào dữ liệu

Explanations:

(a) Between two or more parties and multidirectional; the most efficient way to ensure common understanding

(b) sent to recipients; does not ensure it was actually received and understood

(c) Recipients must access the information; work for large amount of information or large audiences, each recipient accesses at their own discretion

A. (1)&(a), (2)&(b), (3)&(c)

B. (1)&(a), (2)&(c), (3)&(b)

C. (1)&(b), (2)&(c), (3)&(a)

D. (1)&(b), (2)&(a), (3)&(c)

E. (1)&(c), (2)&(a), (3)&(b)

F. (1)&(c), (2)&(b), (3)&(a)

35. Company procedures require the creation of a lessons learned register. Which of following is the best use of lessons learned? -> là các dự án cũ

A. Historical records for future projects

B. Planning record for the current project

C. Informing the team about what the project manager has done

D. Informing the team about the project management plan

36. Which one below situations is not correct when discussing about responsibility Assignment Matrix?  -> chỉ 1 người cho 1 cv

A. Two team members are consulted about the same task

B. Two team members are informed about the same task

C. Two team members are responsible for the same task

D. Two team members are accountable for the same task

37. Downward communication is communication to/from -> Downward là từ cấp trên xuống cấp dưới -> Tới "Direct reports" (nhân viên báo cáo trực tiếp cho bạn).

A. Your senior management

B. Your social groups

C. Your direct reports

D. Your peer

38. You are scheduling an activity which involves a government agency. what type of dependency are you working on?

A. Discretionary

B. Internal

C. Mandatory

D. External

39. True or False: Project manager should consider using milestones for high level reporting -> với các sếp lớn họ chỉ cần cac cột mốc

A. True

B. False

40. What you report project status you compare actual performance to -> so sánh thực tế với kế hoạch

A. The performance of your competitors

B. The performance of previous project

C. The performance of other similar projects

D. The planned performance or baseline

41. True or False: The process improvement Plan is a component of the project management plan that details how project management and development processes are to be analyzed in order to identify how to increase their value -> kế hoach tăng giá trị

A. False

B. True

42. True or False: The Backward pass is used through the activities to determine the critical path & available float of the project -> tính toán lùi

A true

B False

43. Your cost Performance index (CPI) is greater than 1 means you are -> dưới ngân sách, là tốt

A. on Budget

B. under budget

C. over budget

44. To manage a project effectively, work should be broken down into small pieces. Which of the following does not describe how far to decompose the work? -> phân rã công việc, ko nhất thiết phải chia nhỏ đến mức chỉ 1 người

A, Until it has a meaningful conclusion

B. Until it cannot be logically subdivided further

C. Until it can be done by one person

D.Until it can be realistically estimated

45. Which of the following statements is Not likely to be documented in a communications management plan?

A. Person responsible for tracking risk events

B. Time frame and frequency of communication

C. How information will be communicated

D. What information will be communicated

46. True or False: the Project Charter is a document that formally authorizes the existence of a project. it also document initial requirements that satisfy the stakeholder's need and expectations

A. False

B. True

47. Which one of these is not the approaches to conflict discussed in the Project Human Resources Management Lesson?

A. Confronting

B. Compromising

C. Smoothing

D. Forcing

E. Avoiding

F Challenging

48. If a difficult stakeholder has low interest and low power the as the project manager you:

A. Can try to move them to be high interest and high power so that they are happy and di bit get in your way

B. Can try to move them to be high interest and low power so they do not get in your way

C. Can monitor them, but do not bore them with excessive communication

D. Can ignore them, they are as you need them to be

49. Which one of these situations most closely represents scope creep:

A. The project scope changes through the use of a formal change control process

B. The project scope was used to create a WBS that was used to create estimated and a schedule

C.The project scope keeps changing and learn member are not sure why and the project seems like it will never and

D. The scope of the project is clearly agreed upon by they project stakeholders

50. Which item would most likely NOT be part of a basic communication plan:

A. The amount of their annual bonus.

B. What they need to know.

C. With whom to communicate.

D. The best medium for the communication.

51. Upward communication is communication to/from:

A. Your social groups.

B. Your senior management.

C. Your peers.

D. Your direct reports.

52. When you report project status you compare actual performance to:

A. The planned performance or baseline.

B. The performance of your competitors.

C. The performance of previous projects.

D. The performance of other similar projects.

53. You are beginning to staff your project. Which of the following will not be used in developing and/or communicating roles and responsibilities?

A. Organization chart

B. Pareto chart

C. Responsibility Assignment Matrix

D. WBS

54. Which of the following is not likely to be documented in a communications management plan?

A. How information will be communicated

B. What information will be communicated

C. Time frame and frequency of communication

D. Person responsible for tracking risk events

55. A Communications Management Plan does the following:

A. Coordinates the communication between project leaders and uninterested project members

B. Lays out the approach and method for delivering information effectively and efficiently.

C. Coordinates and effort to communicate in meetings effectively

D. Lays out a plan on how to communicate with your Project Sponsor and other organizations

56. Who should take the most responsibility for clear and effective communication?

A. The receiver

B. The Communications Manager

C. The sender

D. The sender and the receiver

57. The purpose of project risk management is to:

A. Minimize the likelihood or the impact of positive events or threats to your project and to increase the likelihood or impact of negative events.

B. Minimize the likelihood or the impact of negative events or threats to your project and to increase the likelihood or impact of positive events.

C. Eliminate the likelihood or the impact of negative events or threats to your project and to decrease the likelihood or impact of positive events.

D. Neutralize the likelihood or the impact of negative events or threats to your project and to neutralize the likelihood or impact of positive events.

58. True or False: A positive risk is an opportunity; a negative risk is a threat.

A. False

B. True

59. When you and your team know that a negative risk has a high likelihood of occurring and it will be very impactful if it does:

A.You should wait a few weeks and see what changes.

B. You should not document the risk; it will upset your stakeholders.

C. You should all hope this risk does not occur.

D. You should develop a response to handle this risk.

60. If the response you choose is to avoid a risk this means that:

A. You simply do not consider the risk.

B. You note the risk but do not talk about it.

C. You change your plans so that you eliminate the risk.

D. You cancel the entire project.

61. Once you and your team identify and assess risks and develop responses you:

A. Pay close attention to the risks identified and do not look for new risks.

B. Only update your risk register when you are preparing to share it with your stakeholders.

C. Have completed your risk management responsibilities.

D. Continue to identify and monitor risks for the remainder of the project.

62. In a project context, risk is defined as:

A. An uncertain event that, if it occurs, will have a positive or negative affect on at least one project objective.

B. The probability of an event having a positive or negative affect on at least one project objective.

C. The impact of not completing the project on time and within budget.

D. An uncertain event that, if it occurs, will have a negative affect on at least one project objective.

63. The Risk Management Plan is a subsidiary to the __________ document.

A. Project Management Plan

B. Project Communications Plan

C. Project Stakeholder Plan

D. Project Scope Statement Plan

64. A useful tool in identifying risks is the SWOT analysis. What does SWOT stand for?

A. Strengths, opportunities, winners, and threats

B. Scope, opportunities, weaknesses, and time

C. Strengths, obstacles, weaknesses, and threats

D. Strengths, opportunities, weaknesses, and threats

65. During a risk brainstorming session a team member identifies a risk. This particular risk does not seem to belong to any of the categories in you Risk Breakdown Structure (RBS). How should you respond?

A. Thank him for his work, but inform him that the risk cannot be included because it does not fit any of the categories defined in the RBS.

B. Record the list in the risk register, discuss potential responses and make a note to update the RBS.

C. Chastise him for making up risks which cannot exist because there is not a category for such risks.

D. Ignore him and move on to another risk identified by a different team member.

66. Which one of these situations most closely represents scope creep:

A. The project scope changes through the use of a formal change control process.

B. The project scope was used to create a WBS that was used to create estimates and a schedule.

C. The project scope keeps changing and team members are not sure why and the project seems like it will never end.

D. The scope of the project is clearly agreed upon by the key project stakeholders.

67. True or False: Unregulated changes allow for innovation and flexibility. Regulating changes causes a lack of creativity.

A. True

B. False

68. Which of these types of changes should be discouraged as a poor project practice:

A. A team member discovers an issue and it makes good business sense to correct the issue as part of the project.

B. A new way to handle a problem is discovered after scope was documented and approved.

C. Because stakeholders did not take the time to define scope earlier in the project.

D. Another project team is doing similar work and is farther along than your project.

69. A good change process will:

A. Have change thresholds that are appropriate for the type of change.

B. Be very complex in order to discourage changes.

C. Allow the project manager to approve all changes.

D. Require the same level of approval for all changes.

70. The purpose of capturing lessons learned is:

A. To capture what went well so that you can recreate the good and to capture what could have gone better so that next time it will go better.

B. To show stakeholders how difficult the project was so that next time their demands will not be so high.

C. To document who performed well on the project and who did not so that poor performers can be punished.

D. To show that you are following project management best practices and therefore you are a superior project manager.

71. To ensure control over the incidence and frequency of change, the project manager establishes a:

A. Work breakdown structure

B. Change control process

C. Responsibility assignment matrix

D. Work procedure schedule

72. Your project team is customer focused and often agrees to incorporate many small scope changes throughout the project execution. The changes are documented in an issues log. Which of the following is not a potential problem?

A. Changes with impacts on cost or time will be elevated to the Change Control Board.

B. Many small changes may accumulate to create trouble for one of the project objectives.

C. Changes may not be integrated across the whole project

D. Management of product specifications and configuration become more difficult.

73. Scope creep results in:

A. Completion delays, decrease in costs, and increase in project complexity.

B. Completion delays, escalation of costs, and decrease in project complexity.

C. Completion delays, escalation of costs, and increase in project complexity.

D. On-time deliverables, escalation of costs, and increase in project complexity.

74. A project manager can defend against scope creep with a good ___________!

A. Change control process

B. Procurement process

C. Project management plan

D. Risk management plan

75. True or False: A positive risk is an opportunity; a negative risk is a threat.

A. True

B. False

76. True or False: A project manager spends 75% of his or her time communicating.

A. False

B. True

77. True or False: Earned value integrates scope, schedule and budget and uses monetary values to assess project status.

A. False

B. True

78. True or False: Effective project communication management creates a bridge between stakeholders based on a shared understanding of the project and the ongoing sharing of information needed for its success.

A. False

B. True

79. During status review meetings to evaluate project performance and progress, which report is NOT preferred to use?

A. Status report

B. Test report

C. Forecasting report

D. Progress report

80. True or False: Once you plan for managing risks, you are not finished. Risk management is an ongoing process.

A. False

B. True (identifying and Risk management is an ongoing process throughout the project)

81. Consider a scenario in which you learn that your project is running two weeks behind schedule. How would you know if is acceptable to be two weeks late?

A. Your variance thresholds should be documented in your project management plan, look there for guidance.

B. Ask your executive management team.

C. If the schedule baseline shows you are two weeks late, then it is not acceptable.

D. If the team tells you the work cannot be completes any earlier that it is acceptable.

82. If develop online modules must be 100% completed before review online modules can begin, that is called a:

A. Finish to start relationship.

B. Finish to finish relationship.

C. Start to finish relationship.

D. Start to start relationship.

83. True or False: A project is defined as being unique and temporary, has an expected output and unlimited resources.

A. True

B. False

84. True or False: Product quality focuses on the goods and services

A. True

B. False

85. If the response you choose is to exploit a risk this means that:

A. You actively do not consider the risk but establish contingency plan.

B. You add steps to your plans to make certain the opportunity is captured.

C. You change your plan so that another party will be responsible for a partial amount of ownership of the opportunity.

D. You create your plan to increase the probability and/or the impact of the opportunity.

86. Earned value integrates budget, quality and scope and uses monetary values to assess project status.

A. True

B. False

87. You are preparing an estimate of the cost for an IT system expansion for a new branch office location. It is a very similar to the IT system expansion undertaken for a branch office that opened six month ago. Which technique might you use if you are pushed for a quick estimate?

A. Analogous

B. Bottoms up

C. Parametric

D. Probabilistic

88. Which one is not the five engagement levels of stakeholders?

A. Leading

B. Neutral

C. Resistant

D. Monitoring

E. Supportive

F. Unaware

("Unaware", "Resistant", "Neutral", "Supportive","Leading")

89. Once the logic of network is laid out, the project manager will product a forward pass and a backward pass through the network. This will provide information regarding ________ and will identify the __________.

A. Resource shortages, high risk activities

B. The high risk activities, non-critical path

C. The slack for each activity, high risk activities

D. The total duration of the project, critical path

90. You are beginning to staff your project. Which of the following will NOT be used in developing and/or communicating roles and responsibilities?

A. Run chart

B. Organization chart

C. Responsibility Assignment Matrix

D. WBS

91. You are building an apartment complex with four. 10,000 square foot buildings based on the same drawings you used another city two year ago. What is the danger of estimating using the same parametric model of $50 per square foot?

A. The Technical design is unstable.

B. It's not very easy to scale.

C. It will take much more time than a bottoms up estimating

D. Historical cost relationships may no longer be applicable.

92. A significant event in a project that may indicate completion of major phase is a/an:

A. Milestone

B. Deliverable

C. Activity

D. Work package

93. During a risk brainstorming session, a team member identifies a risk. This particular risk does not seem to belong to any of the categories in you Risk Breakdown Structure (RBS). How should you respond?

A. Ignore him and move on to another risk identifies by a different team member.

B. Chastise him for his work, but inform him that the risk cannot be included because it does not fit any of the categories defined in the RBS.

C. Thank him for his work, but inform him that the risk cannot be included because it does not fit any of the categories defined in the RBS.

D. Record the list in the risk register, discuss potential responses and make a note to update the RBS.

94. True or False: The primary goal of project risk management is to maximize the likelihood and impact of negative events or threats and to minimize the likelihood and impact of positive events or opportunities.

A. True

B. False

95. You have a stakeholder on your project who has a reputation as being very difficult. He dislikes change and argues against any suggested updates to the way in which his department does their work. The project you are leading is going to significantly impact at least two process used by his team. Which do you think is the best response to this situation?

A. Ignore him and start the project without him. You will include him when you absolutely have to.

B. Ask your sponsor to replace him by another reasonable person.

C. Start the project when you know he's out of town and send him a meeting invite to cover your tracks.

D. Seek him out and begin to open communications with him about what is changing and why.

96. Which one of these is the current view of conflict?

A. Should be a voided

B. Can (and should) be managed

C. Caused by troublemakers

D. Always bad

Current view:

- inevitable

- often beneficial

- natural result of change

- Can (and should) be managed

97. To calculate late finish (LF) of an activity which has more than one successor, you will

A. Take the earliest late start of its immediate successors.

B. Take the earliest late finish of its immediate successors.

C. Take the earliest early finish of its immediate successors.

D. Take the earliest early start of its immediate successors.

98. As you plan your project, you do so thinking that all team members will be assigned to your project for at least 50% of their available time. This is an example of:

A. Wishful thinking

B. Poor planning

C. A project demand

D. An assumption

99. When you use the RACI of Responsible. Accountable, Consult, Inform version of RAM, those who are consulted are:

A. Making the final decision

B. Being kept update about project progress.

C. Providing subject matter expertise

D. Completing the work

100. You just came from a meeting with one of your project stakeholders, he knew about your project and also its potential impacts, and he always supported for the work and its outcome. How would you classify him?

A. Unaware

B. Leading

C. Supportive

D. Neutral

101. True or False: Each person involved in the project should be assigned, but doesn't always need to know his or her role and responsibility.

A. True

B. False

102. True or False: Your role as the project manager during quality control is to implement the quality management plan using the appropriate tools and techniques, in order to ensure that work is being performed according to required quality standards.

A. True

B. False

103. The WBS is used to derive all but one of the following:

A. The project schedule baseline

B. The project cost performance baseline

C. The activity list

D. The business need for the project

104. True or False: A project manager spend 90% his or her time communicating

A. False

B. True

105. True or False: The S-Curve depicts the relationship between the cost baseline budget and the schedule because it shows the planned cost baseline budget across the planned project timeline.

A. False

B. True

106. Which one of these is not the major source of conflict that a project manager may influence

A. Project charter

B. Personality conflict

C. Project schedule

D. Project cost

107. True or False: An important part of the project scope statement is exclusions or out of scope items.

A. True

B. False

108. True or False: Using bottom-up estimating techniques when activity durations or resource quantities are uncertain.

A. False

B. True

109. Because: activity durations or resource quantities are uncertain use top - down estimating techniques.

Bottom-up use for detail is available and accuracy

True or False: Performing quality assurance within the context of a project involves taking actions to eliminate causes of unsatisfactory project performance.

A. False

B. True

110. The three components of the triple constraint are:

A. Scope, Performance, Time

B. Scope, Cost, Time

C. Scope, Performance, Cost

D. Scope, Quality, Cost

111. True or False: The worst organization to use to run a project will always be the functional organization.

A. True

B. False

112. True or False: The sender is responsible to make the information clear, complete, and appropriate to the needs of the receiver. The receiver is responsible to provide feedback to acknowledge that the message has been received and understood.

A. False

B. True

113. True or False: The term resources only refers to people, it does not include money or materials or equipment.

A. False

B. True

114. In our lessons the acronym RAM stands for:

A. Resource Acquisition Management

B. Resource Aligned Management

C. Responsibility Accountability Matrix

D. Responsible Accountable Manageable

E. Responsibility Assignment Matrix

115. When you use the RACI or Responsible, Accountable, Consult, Inform version of the RAM, those who are responsible are:

A. Not completing the work

B. Providing subject matter expertise

C. Supervising the work

D. Completing the work

116. A work package is a/an:

A. Activity that can be assigned to one or more organizational units

B. Activity at the lowest level of the WBS

C. Deliverable at the lowest level of the WBS

D. Required level of reporting

117. The WBS is used to derive all but one of the following:

A. The project schedule baseline

B. The business need for the project

C. The project cost performance baseline

D. The activity list

118. True or False: When it comes to projects, the emphasis is on strategic quality management. Quality is not an accident, quality is part of the plan, and quality is everyone's job.

A. False

B. True

119. The discipline of quality management complements the discipline of project management. Both recognize the importance of:

A. Customer satisfaction, prevention over inspection, continuous improvement, and management responsibility

B. Responsibility of only the sponsor, continuous improvement, and inspection

C. Team satisfaction and inspection over prevention

D. Company satisfaction, continuous improvement, and management protocol

120. True or False: Product quality focuses on the project management processes used to meet project objectives

A. False

B. True

121. The Process Improvement Plan is:

A. A subsidiary, or component of the project management plan.

B. The number one component of the project management plan.

122. True or False: Performing quality assurance within the context of a project involves applying the planned, systematic quality activities to ensure that the project correctly employs all processes needed to meet project objectives and product requirements.

A. False

B. True

123. An estimate created by looking at a similar project or activity and then adding or subtracting to or from the estimate based on the differences between the two is called:

A. Exact estimating

B. Bottoms up estimating

C. Analogous estimating

D. Parametric estimating

124. When you have good historical information which can be used in a reliable formula or model, you will probably use:

A. Parametric estimating

B. Analogous estimating

C. Exact estimating

D. Bottoms up estimating

125. True or False: When you are concerned that your estimates might not be correct, especially if you think they are too low, you should pad the estimate and add extra.

A. False

B. True

126. Which one of these most correctly defines management reserve?

A. Management reserve is not tied to specific work packages it is for the entire project.

B. Management reserve is tied to a specific milestone or event.

C. Per our lesson, management reserve and contingency are exactly the same.

D. Management reserve is tied to specific work packages.

127. You are preparing an estimate of the cost for an IT system expansion for a new branch office location. It is a very similar to the IT system expansion undertaken for a branch office that opened six months ago. Which technique might you use if you are pushed for a quick estimate?

A. Bottoms up

B. Parametric

C. Probabilistic

D. Analogous

128. You are building an apartment complex with four, 10,000 square foot buildings based on the same drawings you used in another city two years ago. What is the danger of estimating using the same parametric model of $50 per square foot?

A. It will take much more time than a bottoms up estimating.

B. It's not very easy to scale.

C. Historical cost relationships may no longer be applicable.

D. The technical design is unstable.

129. What description defines Bottoms Up Estimating?

A. A technique that analyzes activities on past projects and using them as a basis for estimating costs.

B. A technique that uses a mathematical model to estimate costs.

C. A technique that involves estimating the cost of individual work packages or individual schedule activities with the lowest level of detail.

130. True or False: The Project Budget is equal to only the cost baseline budget.

A. False

B. True

131. True or False: The S-Curve depicts the relationship between the cost baseline budget and the schedule because it shows the planned cost baseline budget across the planned project timeline.

A. False

B. True

132. Earned value management integrates scope, cost, and schedule measures to:

A. assess project performance and progress.

B. assess whether all requirements were met.

C. develop a preliminary budget.

D. assess communication effectiveness among project team members

133. When you schedule work in a specific order because it cannot be completed any other way this is what type of dependency?

A. Mandatory

B. External

C. Internal

D. Discretionary

134. True or False: If develop online modules must be 100% completed before review online modules can begin, that is called a finish to start relationship.

A. False

B. True

135. If develop online modules needs to finish before review online modules can finish, that is called a:

A. Finish to start relationship.

B. Finish to finish relationship.

C. Start to finish relationship.

D. Start to start relationship.

136. To calculate early start (ES) and early finish (EF) perform a:

A. Forward pass

B. Lateral pass

C. Critical pass

D. Backward pass

137. True or False: The critical path is the shortest path through the network and represents the work that can be delayed without delaying the end of the project.

A. False

B. True

138. The network diagram is the best tool for demonstrating:

A. The sequence of project activities

B. Schedule performance over time

C. Schedule variances

D. Resource requirements

139. All of the following are inputs to estimating activity durations except:

A. Activity list and activity attributes

B. Organizational process assets

C. Resource calendars and scope statement

D. Requirements specifications

140. In a project schedule, the sequence of activities which cannot be delayed during the course of the project without extending the project end date is referred to as the:

A. Schedule baseline

B. Critical path

C. Action plan

D. Slack line

141. A significant event in a project that may indicate completion of a major phase is a/an:

A. Activity

B. Work package

C. Deliverable

D. Milestone

142. Once the logic of a network is laid out, the project manager will conduct a forward pass and a backward pass through the network. This will provide information regarding ______ and will identify the________.

A. The high risk activities, non-critical path

B. The total duration of the project, critical path

C. Resource shortages, high risk activities

D. The slack for each activity, high risk activities

143. True or False: A project manager spends 75% of his or her time communicating.

A. False

B. True

144. Which item would most likely NOT be part of a basic communication plan:

A. The amount of their annual bonus.

B. With whom to communicate.

C. The best medium for the communication.

D. What they need to know.

145. Upward communication is communication to/from:

A.Your peers.

B. Your senior management.

C. Your direct reports.

D. Your social groups.

146. When you report project status you compare actual performance to:

A. The planned performance or baseline.

B. The performance of previous projects.

C. The performance of your competitors.

D. The performance of other similar projects.

147. True or False: Earned value integrates scope, schedule and budget and uses monetary values to assess project status.

A. False

B. True

148. You are beginning to staff your project. Which of the following will not be used in developing and/or communicating roles and responsibilities?

A. Responsibility Assignment Matrix

B. Organization chart

C. Pareto chart

D. WBS

149. Which of the following is not likely to be documented in a communications management plan?

A. Time frame and frequency of communication

B. What information will be communicated

C. How information will be communicated

D. Person responsible for tracking risk events

150. True or False: Effective project communication management creates a bridge between stakeholders based on a shared understanding of the project and the ongoing sharing of information needed for its success.

A. False

B. True

151. A Communications Management Plan does the following:

A. Lays out the approach and method for delivering information effectively and efficiently.

B. Coordinates the communication between project leaders and uninterested project members

C. Lays out a plan on how to communicate with your Project Sponsor and other organizations

D. Coordinates an effort to communicate in meetings effectively

152. The purpose of project risk management is to:

A. Minimize the likelihood or the impact of negative events or threats to your project and to increase the likelihood or impact of positive events.

B. Minimize the likelihood or the impact of positive events or threats to your project and to increase the likelihood or impact of negative events.

C. Neutralize the likelihood or the impact of negative events or threats to your project and to neutralize the likelihood or impact of positive events.

D. Eliminate the likelihood or the impact of negative events or threats to your project and to decrease the likelihood or impact of positive events.

153. True or False: A positive risk is an opportunity; a negative risk is a threat.

A. False

B. True

154. When you and your team know that a negative risk has a high likelihood of occurring and it will be very impactful if it does:

A. You should develop a response to handle this risk.

B. You should wait a few weeks and see what changes.

C. You should not document the risk; it will upset your stakeholders.

D. You should all hope this risk does not occur.

155. If the response you choose is to avoid a risk this means that:

A. You note the risk but do not talk about it.

B. You cancel the entire project.

C. You simply do not consider the risk.

D. You change your plans so that you eliminate the risk.

156. Once you and your team identify and assess risks and develop responses you:

A. Pay close attention to the risks identified and do not look for new risks.

B. Continue to identify and monitor risks for the remainder of the project.

C. Have completed your risk management responsibilities.

D. Only update your risk register when you are preparing to share it with your stakeholders.

157. In a project context, risk is defined as:

A. An uncertain event that, if it occurs, will have a negative effect on at least one project objective.

B. An uncertain event that, if it occurs, will have a positive or negative effect on at least one project objective.

C. The probability of an event having a positive or negative effect on at least one project objective.

D. The impact of not completing the project on time and within budget.

158. The Risk Management Plan is a subsidiary to the __________ document.

A. Project Scope Statement Plan

B. Project Communications Plan

C. Project Management Plan

D. Project Stakeholder Plan

159. A useful tool in identifying risks is the SWOT analysis. What does SWOT stand for?

A. Strengths, opportunities, winners, and threats

B. Strengths, obstacles, weaknesses, and threats

C. Scope, opportunities, weaknesses, and time

D. Strengths, opportunities, weaknesses, and threats

160. True or False: The primary output from the identification of risks is the risk register.

A. False

B. True

161. During a risk brainstorming session a team member identifies a risk. This particular risk does not seem to belong to any of the categories in you Risk Breakdown Structure (RBS). How should you respond?

A. Chastise him for making up risks which cannot exist because there is not a category for such risks.

B. Thank him for his work, but inform him that the risk cannot be included because it does not fit any of the categories defined in the RBS.

C. Record the list in the risk register, discuss potential responses and make a note to update the RBS.

D. Ignore him and move on to another risk identified by a different team member.

162. Which one of these situations most closely represents scope creep:

A. The project scope keeps changing and team members are not sure why and the project seems like it will never end.

B. The project scope changes through the use of a formal change control process.

C. The scope of the project is clearly agreed upon by the key project stakeholders.

D. The project scope was used to create a WBS that was used to create estimates and a schedule.

163. True or False: Unregulated changes allow for innovation and flexibility. Regulating changes causes a lack of creativity.

A. False

B. True

164. Which of these types of changes should be discouraged as a poor project practice:

A. Another project team is doing similar work and is farther along than your project.

B. Stakeholders did not take the time to define scope earlier in the project.

C. A team member discovers an issue and it makes good business sense to correct the issue as part of the project.

D. A new way to handle a problem is discovered after scope was documented and approved.

165. A good change process will:

A. Require the same level of approval for all changes.

B. Allow the project manager to approve all changes.

C. Have change thresholds that are appropriate for the type of change.

D. Be very complex in order to discourage changes.

166. The purpose of capturing lessons learned is:

A. To capture what went well so that you can recreate the good and to capture what could have gone better so that next time it will go better.

B. To show that you are following project management best practices and therefore you are a superior project manager.

C. To document who performed well on the project and who did not so that poor performers can be punished.

D. To show stakeholders how difficult the project was so that next time their demands will not be so high

167. To ensure control over the incidence and frequency of change, the project manager establishes a:

A. Work procedure schedule

B. Responsibility assignment matrix

C. Change control process

D. Work breakdown structure

168. Your project team is customer focused and often agrees to incorporate many small scope changes throughout the project execution. The changes are documented in an issues log. Which of the following is not a potential problem?

A. Changes with impacts on cost or time will be elevated to the Change Control Board.

B. Changes may not be integrated across the whole project

C. Many small changes may accumulate to create trouble for one of the project objectives.

D. Management of product specifications and configuration become more difficult.

169. True or False: In the context of a project, change is always a bad thing.

A. False

B. True

170. Scope creep results in:

A. On-time deliverables, escalation of costs, and increase in project complexity.

B. Completion delays, escalation of costs, and increase in project complexity.

C. Completion delays, decrease in costs, and increase in project complexity.

D. Completion delays, escalation of costs, and decrease in project complexity.

171. A project manager can defend against scope creep with a good ___________!

A. Project management plan

B. Procurement process

C. Risk management plan

D. Change control process

172. True or False: A Project is defined as being unique and temporary, with an undefined start and finish.

A. False

B. True

173. We discussed three types of matrix organizations, they are:

A. Weak, Medium Strength and Strong

B. Weak, Balanced and Strong

C. Light, Medium and Heavy

D. Light, Mid-strength and Strong

174. In a projectized organization:

A. A project manager is not assigned to the team.

B. The functional manager has all of the power.

C. Team members are never assigned to the project full time.

D. The project manager acts as manager of the team.

175. True or False: The best organization to use to run a project will always be the projectized organization.

A. False

B. True

176. The five project management process groups as described in the PMBOK® Guide and discussed in the preceding lesson are:

A. Initiating, planning, executing, monitoring and controlling, closing

B. Define, measure, analyze, improve, control

C. Kickoff, requirements, plan, schedule, control

D. Requirements, design, development, testing, implementation

177. The three components of the triple constraint are:

A. Scope, Quality, Cost

B. Scope, Performance, Time

C. Scope, Performance, Cost

D. Scope, Cost, Time

178. You have finished planning and have begun executing the project when the client asks if you would add some important features to the product of the project. How are the triple constraints affected?

A. Scope and quality would be affected but not cost

B. Adding features will require additional cost but not time

C. Cost must remain constant because resources are limited

D. Time and cost may both be affected

179. The primary role of the project manager is:

A. Project initiation

B. Distributing work packages

C. Communication

D. Measuring performance

180. As discussed in the preceding lesson, The PMBOK® Guide knowledge areas that have processes in the Initiating process group are:

A. Project Integration Management and Project Scope Management

B. Project Integration Management and Project Stakeholder Management

C. Project Integration Management and Project Time Management

D. Project Integration Management and Project Quality Management

181. As discussed in the preceding lesson, The PMBOK® Guide describes 10 Project Management Knowledge Areas. Identify 3 out of the 10:

A. Cost, Integration, Process

B. Cost, Scope, Time

C. Quality, Process, Scope

D. Contracts, Process, Risk

182. The definition of a stakeholder includes:

A. People who are impacted by your project, but not organizations impacted by your project.

B. The people or organizations that are positively or negatively impacted by your project.

C. Organizations impacted by your project but not people, they are all part of the impacted organizations.

D. People and organizations that are not impacted by your project.

183. True or False: If you are not certain who your stakeholders are, asking who will use the product or service being created can be helpful.

A. False

B. True

184. If a stakeholder has high interest and high power then as the project manager you:

A. Can try to move them to be high interest and low power so they do not get in your way.

B. Focus your time and attention on them, they are very impactful to your project and you want to keep them engaged and positive.

C. Can try to move them to be low interest and low power so that they do not take up too much of your time.

D. Can ignore them, they are as you need them to be.

185. You just came from a meeting with one of your project stakeholders, he knew about your project and was not against it, but did not seem to be particularly interested in it either. How would you classify him?

A. Unaware

B. Resistant

C. Neutral

D. Supportive

186. True or False: The Project Sponsor is responsible for stakeholder expectations management.

A. False

B. True

187. Who is the stakeholder that will ultimately use the product or service you are creating?

A. Project Team

B. Sponsor

C. Customer/User

D. Project Manager

188. One way to classify your stakeholders is to use the Power/Interest Grid. If a stakeholder is low interest / low power, what should the Project Manager do?

A Manage closely

B. Keep informed

C. Keep satisfied

D. Monitor

189. Your stakeholder register is your primary output and should at least contain:

A. Job descriptions, identification information, and stakeholder classification

B. Assessment information, scope information, and stakeholder classification

C. Assessment information, identification information, and stakeholder classification

D. Assessment information, identification information, and risk classification

190. You have a stakeholder on your project who has a reputation as being very difficult. He dislikes change and argues against any suggested updates to the way in which his department does their work. The project you are leading is going to significantly impact at least two processes used by his team. Which do you think is the best response to the situation?

A. Seek him out and begin to open communications with him about what is changing and why.

B. Start the project when you know he's out of town and send him a meeting invite to cover your tracks.

C. Ignore him and start the project without him. You will include him when you absolutely have to.

191. Identify the five engagement levels of stakeholders:

A. Unaware, resistant, neutral, supportive, oblivious

B. Unaware, resistant, strong-willed, supportive, sponsor

C. Unaware, resistant, neutral, supportive, leading

D. Unaware, resistant, strong-willed, supportive, leading

192. One of the ways a Project Charter can help you as a project manager is:

A. It describes your authority level as the project manager.

B. It keeps your authority level vague, so you can do what you want.

C. It does not help you as a project manager because it is for the sponsor.

D. It helps you hire team members.

193. The Scope Management section of your project plan document would include information on:

A. What type of scheduling software to use.

B. How risks are to be managed.

C. Who can suggest changes to the project.

D. How to ask for more money for the project.

194. True or False: An important part of the project scope statement is exclusions or out of scope items.

A. False

B. True

195. As you plan your project, you do so thinking that all team members will be assigned to your project for at least 50% of their available time. This is an example of:

A. Wishful thinking.

B. An assumption.

C. A project demand.

D. Poor planning.

196. True or False: The WBS should completely depict the scope of your project that if something is not in the WBS it is because it is NOT part of the project.

A. False

B. True

197. The 8-80 rule refers to:

A. Work packages should NOT be between 8 and 80 hours of effort.

B. Never allow your team to work more than 8 hours per day or 80 hours during a 10-day work period.

C. Work packages should be between 8 and 80 hours of effort.

D. Work packages over 80 hours should be split between multiple resources.

198. Project scope differs from product scope in that:

A. Project scope completion is measured against the features, functions, and product requirements.

B. Project scope is the work that needs to be accomplished to deliver a product, service, or result.

C. Product scope completion is measured against the project management plan including all subsidiary plans.

199. True or False. The Project Charter is a document issued by the project initiator or sponsor that formally authorizes the existence of a project. It provides the project manager with the authority to apply organizational resources to project activities.

A. False

B. True

200. The Project Scope Statement should include the following:

A. Project exclusions, project constraints, project plan.

B. Project deliverables, project constraints, project assumptions.

C. Project deliverables, project constraints, project team members.

D. Project exclusions, project charter, project assumptions.

201. True or False: A Work Breakdown Structure (WBS) is a deliverable-oriented hierarchical decomposition of the work to be executed by the project team.

A. False

B. True

202. True or False: Influence means you have the right to apply resources, make decisions and give approvals.

A. False

B. True

203. Which one of these is an example of role conflict:

A. When a team member does not know why he or she should do something.

B. When two team members are trying to complete the same task.

C. When a team member is late completing a task.

D. When a team member does not know how to do his or her job.

204. Two team members disagree on how to solve a project issue. They express their disagreement and then engage in a professional debate. This is an example of:

A. Unhealthy conflict.

B. Unrealistic conflict.

C. Unproductive conflict.

D. Healthy conflict.

205. You and another project manager disagree over whether a team member should work on your team or on her team. You decide that the team member can work for the other project manager in the afternoon and the other project manager says it is OK for the team member to work for you in the morning. The truth is you both wanted this person fulltime. The conflict resolution approach you have both used is:

A. Compromising

B. Confronting

C. Smoothing

D. Forcing

206. True or False: Conflict management is the process by which the project manager uses appropriate managerial techniques to deal with the inevitable disagreements that develop among those working toward project accomplishment.

A. False

B. True

207. Some of the major sources of conflict that a project manager may influence are:

A. Project management, project priorities, project team

B. Personality conflict, schedules, resources

C. Project charter, schedules, resources

D. Personality conflict, network diagram, resources

208. What are the 5 approaches to conflict discussed in the Project Human Resources Management Lesson?

A. Confronting, Challenging, Smoothing, Forcing, Avoiding.

B. Confronting, Compromising, Smoothing, Forcing, Avoiding.

C. Confronting, Compromising, Smoothing, Uninterested, Challenging.

D. Communicating, Compromising, Smoothing, Forcing, Avoiding.

209. True or False: Project Human Resource Management includes the processes that organize, manage, and lead the project team.

A. False

B. True

210. True or False: Each person involved in the project should be assigned, but doesn't always need to know his or her role and responsibility.

A. False

B. True

211. What does RAM stand for:

A. Responsibility Ambiguity Matrix

B. Responsibility Assignment Matrix

C. Responsibility Activity Matrix

D. Responsibility Action Matrix

212. An important part of the project scope statement is exclusions or out of scope items.

A. True

B. False

213. Which one of these is an example of role conflict:

A. When two team members are trying to complete the same task.

B. When a team member does not know why he or she should do something.

C. When a team member is late completing a task.

D. When a team member does not know how to do his or her job.

214. Two team members disagree on how to solve a project issue. They express their disagreement and then engage in a professional debate. This is an example of:

A. Healthy conflict.

B. Unproductive conflict.

C. Unhealthy conflict.

D. Unrealistic conflict.

215. You and another project manager disagree over whether a team member should work on your team or on her team. You decide that the team member can work for the other project manager in the afternoon and the other project manager says it is OK for the team member to work for you in the morning. The truth is you both wanted this person fulltime. The conflict resolution approach you have both used is:

A. Forcing

B. Compromising

C. Smoothing

D. Confronting

216. Conflict management is the process by which the project manager uses appropriate managerial techniques to deal with the inevitable disagreements that develop among those working toward project accomplishment.

A. False

B. True

217. Some of the major sources of conflict that a project manager may influence are:

A. Project management, project priorities, project team

B. Personality conflict, schedules, resources

C. Personality conflict, network diagram, resources

D. Project charter, schedules, resources

218. What are the 5 approaches to conflict discussed in the Project Human Resources Management Lesson?

A. Confronting, Challenging, Smoothing, Forcing, Avoiding.

B. Confronting, Compromising, Smoothing, Forcing, Avoiding.

C. Confronting, Compromising, Smoothing, Uninterested, Challenging.

D. Communicating, Compromising, Smoothing, Forcing, Avoiding.

219. Project Human Resource Management includes the processes that organize, manage, and lead the project team.

A. True

B. False

220. Each person involved in the project should be assigned, but doesn't always need to know his or her role and responsibility.

A. True

B. False

221. One of the ways a Project Charter can help you as a project manager is:

It describes your authority level as the project manager

222. The scope management section of your project plan document would include information on:

Who can suggest changes to the project

223. True or False: An important part of the project scope statement is exclusions or out of scope items

A. True

B. False

224. As you plan your project, you do so thinking that all team members will be assigned to your project at least 50% of their available time. This is an example of:

An assumption

225. True or False: The WBS should completely depict the scope of your project that if something is not in the WBS it is because it is NOT part of the project

A. True

B. False

226. The 8-80 Rule refers to:

Work packages should be between 8 and 80 hours of effort

227. Project scope differs from product scope in that:

Project scope is the work that needs to be accomplished to deliver a product, service, or result

228. True or False: The project Charter is a document issued by the project initiator or sponsor that formally authorizes the existence of a project. It provides the project manager with the authority to apply organizational resources to project activities

A. True

B. False

229.The Project Scope Statement should include the following:

Project deliverables, project constraints, project assumptions.

230. True or False: A Work Breakdown Structure (WBS) is a deliverable-oriented hierarchical decomposition of the work to be executed by the project team.

A. True

B. False

231. The definition of a stakeholder includes:

The people or organizations that are positively or negatively impacted by your project

232. True or False: If you are not certain who your stakeholders are, asking who will use the product of service being created can be helpful.

A. True

B. False

233. If a stakeholder has high interest and high power then as the project manager you:

Focus your time and attention on them, they are very impactful to your project and you want to keep them engaged and positive

234. True or False: The Project Sponsor is responsible for stakeholder expectations management

A. True

B. False

235. Who is the stakeholder that will ultimately use the product or service you are creating?

Customer/User

236. One way to classify your stakeholders is to use the Power/Interest Grid. If a stakeholder is low interest / low power, what should the Project Manager do?

Monitor

237. Your stakeholder register is your primary output and should at least contain:

Assessment information, identification information, and stakeholder classification

238. You have a stakeholder on your project who has a reputation as being very difficult. He dislikes change and argues against any suggested updates to the way in which his department does their work. The project you are leading is going to significantly impact at least two processes used by his team. Which do you think is the best response to the situation?

Seek him out and begin to open communications with him about what is changing and why

239. Identify the five engagement levels of stakeholders:

Unaware, resistant, neutral, supportive, leading

240. While looking at the project cost baseline graph shown below, a project manager sees that the stair-step line's last point is higher than the estimate at completion (EAC). What does this relationship mean for the project?

A. The project is running over budget

B. The management reserve is too large

C. Total funding for the project exceeds the project's anticipated needs

D. The project is behind schedule

241. Your company has just been awarded the contract for an important research project. The CEO of your company has asked you, as the project manager, to create the project charter and send it to her so that she can review and approve it. To create the project charter, you need the project's statement of work (SOW). What should you do?

A. Create the SOW yourself since you are the project manager

B. Look for the SOW in your organizational process assets (OPAs)

C. Ask your customer to provide you with the SOW

D. Ask your CEO to provide you with the SOW

242. A project manager is leading a project to investigate the feasibility of constructing a dam to generate hydroelectric power. The project needs to be analyzed from technical, economic, and social points of view. The project manager has created the project charter on behalf of the project sponsor, and it is now approved. Which of the following processes should be performed next?

A. Develop Project Management Plan

B. Identify Risks

C. Identify Stakeholders

D. Develop Project Charter

243. You are managing a software upgrade project for your company. Your project sponsor has a great deal of authority regarding project decisions, but you recently discovered that he doesn't have much interest in your project. To complete the project successfully, you need your project sponsor's continuous support. What stakeholder management strategy should you use with your project sponsor?

A. Keep the sponsor satisfied

B. Manage the sponsor closely

C. Monitor the sponsor's actions

D. Keep the sponsor informed

244. A project manager is leading the construction of a new office building. The project sponsor asks the project manager to email him a project document that was presented during the last project status meeting. The project sponsor states that he has forgotten the name of the document, but he remembers it contained the description, owner, source, priority, and status of product requirements. Which project document is the project sponsor requesting?

A. The requirements management plan

B. The requirements traceability matrix

C. The scope management plan

D. The work breakdown structure (WBS)

245. You are facing problems decomposing the testing work package into the final activities required to complete the work package. Detailed testing plans and activities cannot be determined until the system is at least 50% developed and more details become available. The system development work package will take at least three months to complete. What is the best way to resolve this problem?

A. Use product analysis techniques such as product breakdown and systems analysis to decompose the system testing work package

B. Decompose the system development work package now and decompose the system testing work package later

C. Break down the project into multiple phases so that the system testing work package goes into the second project phase

D. Consult the project management plan to determine what to do in this situation

246. You are managing a project in Alaska to extend an existing oil pipeline, and you are about to start project planning. Due to the large size of the project along with the regulatory and environmental considerations, the development of a detailed project management plan will be critical. As a starting point for initial project planning, what is the first thing you should do?

A. Conduct a project kick-off meeting to inform and engage stakeholders and gain commitment

B. Review the project charter to understand the high-level information about the project

C. Begin the process of identifying stakeholders so they can be engaged as necessary for project planning

D. Share the project scope statement with the project team for a common understanding of project deliverables

247. You are a project manager planning a project to develop a new payroll system, and you are currently in the process of determining, documenting, and managing stakeholder needs and requirements to meet project objectives. A project stakeholder has suggested that it would be helpful to have a visual depiction showing how people and other systems will interact with the new payroll system. You like the idea and want to address it. What is the best way to implement the stakeholder's suggestion?

A. Develop a context diagram

B. Design an affinity diagram

C. Create a fishbone diagram

D. Build a matrix diagram

248. Recently, you promoted your star programmer, Sam, to lead the development team. Sam was a fantastic software coder, and you thought the promotion would mean that he could now share his expertise with the other development team members. However, you are surprised to learn that the performance of Sam in his new role is not meeting your expectations. Which empirical rule did you forget while considering the promotion of Sam?

A. Expectancy theory

B. Peter principle

C. Pareto concept

D. Murphy's law

249. You have just taken over a project to overhaul the company's telecommunications network. During your first week, you determine that the engineers spend at least 80% of their time responding to unexpected requests for information from different project stakeholders. Because of these interruptions, your engineers cannot focus on their assigned project activities, which is resulting in frequent network outages. What should you do first?

A. Immediately tell the engineers to stop responding to unexpected requests since it is not their responsibility

B. Push the engineers to respond to all the requests faster so that they can perform their assigned project activities

C. Ask the engineers to forward all stakeholder inquiries to you so that they can focus on their originally planned tasks

D. Review the communications management plan to understand how stakeholder requests should be handled

250. You are managing a project to develop a new robot for a mining rescue company. You are currently performing a monitoring and controlling project activity, and you have discovered that some of the project work has not been performed according to the plan. If these issues are not fixed before the next customer inspection, your project might be canceled. You have analyzed the situation, and the corrective action will only require a minor adjustment to a configuration element. What should you do first?

A. Implement the corrective actions

B. Submit a change request

C. Consult the project sponsor

D. Delay the scheduled customer inspection

251. A project manager is leading a process improvement project for a factory operation. Currently, the project manager and the team are performing the Monitor and Control Project Work process. Which of the following activities might the project manager and the team conduct during this process?

A. Comparing actual project performance against the project management plan

B. Implementing approved change requests to achieve the project's objectives

C. Analyzing change requests and either approving or rejecting them

D. Gaining formal acceptance of the deliverables by the customer or sponsor

252. You are employed by a software development company as a project manager. Your company has a policy that a change control board (CCB) reviews all of the change requests for every project in your organization, and the CCB follows all the recommended activities outlined in the PMBOK® Guide. You and your project team do not serve as members of the CCB. Based on this scenario, which of the following activities might be performed by members of the CCB?

A. Creating a change request

B. Implementing approved change requests to achieve the project's objectives

C. Evaluating changes to project artifacts not specified in the configuration management plan

D. Monitoring implementation of approved change requests as they occur

253. You are managing a hotel construction project, and you have asked your project team to calculate the current earned value metrics to determine the project performance. Your team reports back that the project's to-complete performance index (TCPI) is 0.9 based on the budget at completion (BAC). Which of the following is true regarding your project's current situation as reflected by this TCPI value?

A. The project is within budget

B. The project is over budget

C. The project is behind schedule

D. The project is ahead of schedule

254. You are working with your team on estimating how much time each activity will take. One of the documents you are using contains information on categories of labor, material, and equipment required to complete your project. You are also interested to see skill levels of your labor, any certifications required, and grade levels of your supplies. Which of the following documents would you primarily refer to for this purpose?

A. Resource breakdown structure

B. Organizational breakdown structure

C. Work breakdown structure

D. Risk breakdown structure

255. You are managing an engineering design project. The vendor has created 50 engineering drawings. Since the project is on a tight schedule and budget, checking every drawing for accuracy and completeness would be impossible. You direct the team to randomly select 20 drawings for inspection. This exercise can best be described as an example of:

A. Inspection

B. Statistical sampling

C. Attribute sampling

D. Control charting

256. During an inspection of a project deliverable, the team detects the same defect in the deliverable that has already been identified during a previous inspection. The project manager is confused how this could have happened since a change request was approved to correct the defect. After discussing the issue with the team, the project manager learns that the team never implemented the approved change request. What could have helped prevent this situation?

A. Holding an approved change requests review

B. Conducting a retrospective meeting

C. Performing a root cause analysis

D. Creating a quality report

257. After taking over a project that is in the middle of execution, you are looking for information about the quality management issues that have been escalated by the team and any corrective actions that have been recommended and/or implemented. What should you do?

A. Look at the issue log

B. Check the quality management plan

C. Review the quality reports

D. Talk to the previous project manager

258. A project manager is leading a project to streamline the manufacturing process of modular homes. The project manager researches and discovers a set of technical guidelines that will make the homes easier and cheaper to manufacture without compromising quality. The team incorporates these guidelines by designing a new modular home that reduces the total number of parts and uses more standard and multi-functional components. This is an example of:

A. Problem solving

B. Design for X

C. Change request

D. Data gathering

259. You are a project manager for a national consumer goods retailer. Currently, you are about to start the development of the assumption log for a project to build a new retail store. What should you do first?

A. Examine the project management plan

B. Start the Identify Stakeholders process as the assumption log is an output of this process

C. Review the project scope statement

D. Read the project business case

260. You are managing a project to update the packaging and digital media for a popular snack food to promote a charity fundraiser. The project is well underway, and you are currently actively collecting and storing information about each deliverable team's progress, creating forecasts for your sponsor, distributing work performance reports and planning presentations to key stakeholders, and verifying delivery. Which process are you performing?

A. Manage Communications

B. Monitor Communications

C. Manage Stakeholder Engagement

D. Plan Communications Management

261. The following table is an activity list that includes the duration and predecessor for a series of project activities. What is the duration of the critical path?

A. 11

B. 14

C. 9

D. 13

262. A project manager is about to start planning a software development project. The project sponsor would like to review any project risks that have been identified at this point. Which document should the project manager recommend the sponsor to review?

A. Project charter

B. Issue log

C. Risk register

D. Risk report

263. You have recently been assigned to lead a project that is halfway into execution. The project has many stakeholders, and you are trying to determine how to engage them effectively. Which of the following will best help you in this effort?

A. Project management plan

B. Project charter

C. Work performance reports

D. Procurement documents

264. As a project manager, you are in the process of establishing a knowledge management system for your project. Which of the following actions will be the least beneficial in this process?

A. A review of the lesson learned register

B. Reading the requirements documentation

C. An examination of the resource breakdown structure

D. Studying the project team assignments

265. Two new team members have just joined the project you are leading. The project is large and involves many stakeholders. You want to get the new team members up to speed with the overall dynamics of the project and engage effectively with the project stakeholders. What should you do?

A. Ask the team members to record any issues they encounter into the issue log

B. Review the stakeholder register with the new team members

C. Schedule a meeting with the new team members and all project stakeholders

D. Submit a change request to update the stakeholder engagement plan

266. A project manager had originally planned to use both of the company's industrial 3D printers simultaneously for a project but has just learned that one of them will be unavailable. The project manager adjusts the schedule so that the components are created sequentially using the one remaining 3D printer. Unfortunately, this action affects the critical path and delays the planned finish date of the project. What tool or technique has the project manager used in this situation?

A. Fast tracking

B. Resource smoothing

C. Crashing

D. Resource leveling

267. A new project is starting, and the team members come from all over the world. The project manager has concerns about communications. What should the project manager do first?

A. Implement an online tool to enable the team members to chat among themselves

B. Enroll the project team members in cultural training to raise cultural awareness

C. Nothing; the business world has been multicultural for so long that there should be no issues

D. Funnel all communications through the project manager to avoid miscommunication

268. Midway into project execution, one of your senior project team members is leaving the company. Due to a delay in filling the position, you have decided to assign the affected tasks to two less experienced employees. Which factor would most strongly affect the duration of their assigned tasks?

A. Parkinson's law

B. Student syndrome

C. Law of diminishing returns

D. Number of resources

269. You are leading a project to build an oil pipeline in a foreign country, and you are looking for local contractors to outsource some of the construction work. You are in the process of preparing the bid package for prospective sellers. Which of the following documents would you leave out of the package?

A. Request for proposal

B. Statement of work

C. Independent cost estimates

D. Source selection criteria

270. You are developing the communications management plan for a construction project. You want to determine the information needs of the project stakeholders, specifically focusing on the type and the format of information that will be required to communicate with the stakeholders. What is your best course of action?

A. Develop the stakeholder register

B. Review the requirements documentation

C. Conduct a communication requirements analysis

D. Consult the stakeholder engagement plan

271. You are managing the development of a new blood pressure cuff for a customer who provided you with the objectives and description of the cuff. You and your team are decomposing the customer's high-level requirements to the level of detail needed to design the blood pressure cuff and therefore define the scope of the product. In what activity are you involved?

A. Technical performance analysis

B. Create WBS

C. Define Activities

D. Product analysis

272. Your risk report shows that project risk exposure overall has grown close to a negative threshold. Before the next regular meeting, you ask risk owners to present any risks and opportunities that may affect short-term activities. In the meeting, it becomes clear that risk owners from less engaged departments did not implement some of the previously approved responses. What should you do now to reduce risk exposure?

A. Submit a change request to exploit an opportunity that potentially makes up for the undone risk responses

B. Privately confront the risk owners with the issue and collaborate to remove any impediments to the risk responses

C. Reassign the risk ownership to team members who are in departments that are more engaged in the project

D. Escalate the issue by calling a meeting with the risk owners and their managers to discuss disciplinary measures

273. As part of the process to develop the scope statement for the project you are leading, you specify the deliverables for the project, include the requirements under which the deliverables will be accepted, and explicitly state what is out of project scope. What should you do next?

A. Obtain approval of the project scope statement

B. Include the acceptance criteria in the scope statement

C. Determine who decides the project is successful

D. Describe product scope in the scope statement

274. With the start of project execution, a project manager needs to acquire the development team. However, the project sponsor indicates that of those developers who were planned for the project, one is unavailable as she is currently completing another project. What should the project manager do to understand the proposed team member's future availability?

A. Look at the project documents

B. Contact the team member's functional manager

C. Review the resource requirements

D. Examine the resource breakdown structure

275. Up until now, your project team has allowed the use of flextime where project team members may take time off during regular business hours and make up the time during the evening hours or weekends. Recently, excessive use of flextime has become a roadblock as some team members are not available when needed. The team feels they should set a standard that flextime is only to be used for personal emergencies. How should you handle this situation?

A. Contact the human resources department to update the corporate policies to prohibit flextime

B. Submit a change request to update the team charter based on the team's inputs

C. Discuss the issue with the team and update the team charter accordingly

D. Do nothing as the team has already agreed to use flextime for personal emergencies only

276. You work with your team to sequence activities on the project you are leading. You are looking for the factors, constraints, and potential dependencies among project activities that can influence the way activities are sequenced, as well as help you understand the relationship between activities and the need for leads and lags. Where could you find this information?

A. Basis of estimates

B. Work breakdown structure

C. Assumption log

D. Project schedule

277. You have completed a nine-month project, and you are in the closing stage. The project completed on time and under budget and everyone in your department has congratulated you on your achievement. The vice president of your company heard about the success of your project and wants a summary overview of project performance so that he can talk about your success at the next board meeting. What should you provide to him?

A. Lessons learned repository

B. Project closure documents

C. Final lessons learned register

D. Final report

278. As a project manager, you are leading a software development project where the developers are colocated within rented office space. Writing the code is taking longer than anticipated, and you have contacted the office facility to ensure the office will be available for another week. Unfortunately, the office is already booked, so you need to find another solution. After capturing the problem in the project documents, what should you do next?

A. Record the issue in the issue log

B. Revise the resource management plan

C. Update the schedule baseline

D. Request additional funds

279. A project manager is conducting the initial process of identifying stakeholders for a new infrastructure development project. The project manager has just compiled a list of potential stakeholders' names. What should the project manager do next?

A. Invite the identified stakeholders to the project kick-off meeting

B. Conduct stakeholder analysis

C. Complete the Project Stakeholder Management process

D. Develop the stakeholder engagement plan

280. You are leading a project to construct a new runway at an existing commercial airport. After completion of the project, the residents under the flight path of the new runway are making noise complaints and want the airport to compensate them for the diminished values of their homes. What might you have missed earlier in the project?

A. Including in the stakeholder register those with a contribution stake in the project

B. Stakeholder analysis including consideration for those with an interest stake in the project

C. A thorough review of the agreements prior to the development of the stakeholder register

D. The inclusion of the affected homeowners in the project charter

281. Following is an illustration of a project network activity node that includes some information about activity D. Given the information provided, what is the total float of activity D?

A. 2

B. 14

C. 16

D. 18

282. During a bidder conference, a supplier asks why a section is missing from the request for quotation (RFQ). The project manager, realizing that an aspect of the project is indeed missing, becomes flustered and stumbles through a brief reply. When the seller responses were received, all but three fail to address the missing section. What is the best course of action?

A. Hold the bidder conference again, and explain the importance of the point that was initially missed

B. Select from the three vendors that submitted complete proposals

C. Send a revised RFQ to all prospective suppliers and allow them the opportunity to resubmit their proposals

D. Extend the deadline and allow all of the vendors to resubmit their proposals

283. You are leading a project to develop a new web application. Together with your project team you reprioritize the product backlog, determine velocity for the past iterations, and adapt your work plans accordingly. Additionally, you facilitate retrospectives every two weeks. Which of the following processes describes the work you are performing?

A. Monitor Risks

B. Manage Quality

C. Control Schedule

D. Develop Schedule

284. You are part of a cross-functional organizational development team, piloting an adaptive approach to project management in an organization that has traditionally used a predictive approach. You realize that you have to tailor the template of the schedule management plan. Which of the following components of the template are you likely to tailor the most?

A. The rules of performance measurement, the summary milestones, and the key deliverables

B. The organizational procedures links, the units of measure, and the project organization charts

C. The schedule model development, the release and iteration length, and the reporting formats

D. The project schedule model maintenance, the level of accuracy, and the level of precision

285. Your boss is giving you a rough outline of the scope, constraints, and risks involved in a prospective client's project. The project is highly similar to another project you are currently closing. The sponsor wants to know how long this project would take your team to complete. You think your team may need two months, but what should your answer be?

A. "Let me run some numbers in a simulation, and get back to you tomorrow."

B. "Give us two months. We will knock it out just like the project that we are closing now."

C. "If it truly resembles this project we are closing, it could be six to ten weeks."

D. "Considering the uncertainty in scope, I estimate three months."

286. A project team performs monthly risk audits for a project in which a large number of identified risks have been realized. So far, the risk responses have been appropriate, and reserves are sufficient. An executive for the requesting organization chides the project manager for doing risk audits improperly, stating that like all audits, outside independent resources need to perform risk audits. How should the project manager respond?

A. Explain that risk audits can be performed either internally or externally as long as they follow the project management plan

B. Agree with the executive and submit a change request to update the project management plan to have the audits conducted externally

C. Follow the guidance provided by the executive and hire a team of external auditors to conduct the risk audits going forward

D. Explain that if the current risk audits are not sufficient, then a comprehensive project audit should be carried out

287. With a parking garage construction project underway, you are currently creating the risk management plan. In support of this process, you need to determine the acceptable level of overall project risk exposure. What should you do first?

A. Determine the risk appetites of key project stakeholders

B. Consult the risk exposure register within the organizational process assets

C. Facilitate a brainstorming meeting to develop a comprehensive list of project risks

D. Develop a set of responses to individual project risks to mitigate overall project risk

288. A project manager has just learned that the customer is not showing up to requirements meetings saying they have other more important tasks. Since this behavior has already been identified as a risk earlier in the project, the project manager escalates the issue to the stakeholder who is the risk owner responsible for communicating with the customer in such situations. The stakeholder is shocked to find out she is the assigned risk owner. What most likely went wrong?

A. The stakeholder register had the wrong risk owner

B. The project manager did not follow the risk management plan

C. The stakeholder has not read the risk register

D. The project manager did not notify the stakeholder that they were the risk owner

289. A project is underway to construct a 50 story office building. With construction nearly complete, a government inspector has issued a stop order because one of the cranes failed inspection. The schedule reserves are inadequate to cover the resulting delay from the unavailability of the key resource. What should the project manager do next?

A. Update the resource management plan

B. Submit a change request to update the schedule baseline

C. Submit a change request to update the cost baseline

D. Terminate the project since the project objectives cannot be met

290. A project manager notifies the project sponsor that the mitigation strategy for a major risk did not work. The sponsor states that the same risk response was implemented a few months ago on a similar project with the same result. How might this situation have been avoided?

A. The project manager should have researched the lessons learned register for knowledge gained throughout similar past projects

B. The project manager should have applied the avoidance risk response strategy because the risk had been seen before in past projects

C. The project manager should have researched the lessons learned repository for knowledge gained throughout similar past projects

D. The project manager could not have avoided this situation since it is impossible to determine in advance the effectiveness of a risk response

291. You are planning a project to construct a luxury condominium complex that will include jacuzzi tubs among its numerous features. Due to technical constraints, it has been decided to eliminate the jacuzzi tubs from the final project requirements. You document the jacuzzi tubs as an explicit scope exclusion in the project scope statement as well as update the requirements documentation to reflect this change. What should you do next?

A. Reflect the scope exclusion in the requirements traceability matrix

B. Document the status of the change in the change log

C. Record the elimination of the jacuzzi tubs as an issue in the issue log

D. Capture the exclusion of the jacuzzi tubs in the exclusion register

292. You are managing the development of a new smartphone in an extremely competitive market. You are planning the must-have features of the smartphone in detail so that work can begin and the product can be released to the market as early as possible. The future features are unknown at the moment and will depend on what the competitors release. You will plan these features in greater detail later on. As you and your team create the work breakdown structure (WBS), what will you use to indicate the future features?

A. Control accounts

B. Rolling wave planning

C. Work packages

D. Planning packages

293. A project to construct a new subway line is underway, and the tunnel boring machine has slowed due to unexpected changes in rock composition. It has been decided to implement the planned risk response by increasing the speed of the machine to 100% of rated capacity. The team believes that the additional strain on the machine will not cause more downtime for its maintenance thus negating the benefit of faster boring. What should the project manager do first?

A. Revise the assumption log

B. Order another machine as a backup

C. Update the schedule baseline

D. Update the lessons learned register

294. The project you have been managing for several years is now moving towards completion. Some of the project deliverables have been contracted to vendors. You begin to close the project and want to make sure all activities necessary for project closure are properly completed. Which of the following activities would you not perform as part of this process?

A. Reviewing the project exit criteria

B. Measuring stakeholders' satisfaction

C. Ensuring all costs are charged to the project

D. Closing procurements with vendors

295. While working to determine the budget for an avionics project, the company decides to hire a highly reputable financial analyst that has worked in the aviation industry for three decades. Halfway through the project, a series of unanticipated risk events occur, and the project cannot pay its invoices. What is most likely to be the cause?

A. The control accounts were not correctly established

B. The analyst did not identify risks properly

C. Funding limit reconciliation was done incorrectly

D. The management reserves were exhausted

296. You are part of the project team designing a new type of subway car. You have completed the last work package for the braking system; however, you are not sure what the acceptance criteria are for this particular work package. Where can you find that information?

A. The project management plan

B. The project scope statement

C. The requirements documentation

D. The WBS dictionary

297. You are leading a project team with a technology upgrade project within a project-oriented organizational structure. You were recently informed that one of your project team members falsified required certifications on their resume', and you have verified the information as accurate. You want to terminate the team member's employment. What should you do first?

A. Refer the issue to the employee's functional manager

B. Seek guidance from the resource management plan

C. Immediately terminate the employee for cause

D. Review the enterprise environmental factors

298. During a recession, a project manager posts a positive risk that in the current economic environment, cheaper resources may become available. On the way into work, the project manager hears about a competitor going out of business and contacts the competitor to acquire some equipment, materials, and supplies at a fraction of their normal value. What is the project manager doing?

A. Executing a mitigation plan

B. Reacting to a contingency plan trigger

C. Transferring an identified risk

D. Sharing a realized positive risk

299. A project manager is identifying stakeholders for a new product development project. Which of the following activities is the project manager least likely to perform in the creation of the stakeholder register?

A. Assess any available project documentation and lessons learned from past projects

B. Perform stakeholder analysis to develop a list of stakeholders with relevant information

C. Submit a change request to update the stakeholder engagement plan

D. Categorize the stakeholders' stakes including interest, rights, ownership, and contribution

300. A project manager is facilitating a first brainstorming session to identify individual risks as well as sources of overall project risk. The meeting attendees are struggling with the task, and the meeting is becoming unproductive. What action might the project manager take to get the meeting back on track?

A. Use the RBS as a prompt list

B. Consult the risk register

C. Adjourn the meeting

D. Call in the project sponsor

301. You are establishing the relative priorities of individual project risks that have been identified earlier in the project. Which of the following tasks are you least likely to perform?

A. Review the assumption log

B. Examine the risk register

C. Research the stakeholder register

D. Create the risk report

302. A previously unknown risk surfaces on a project and creates an issue that is estimated to cost $50,000. The project manager submits a change request to adjust the schedule baseline and uses the already approved contingency reserves to address the cost. What did the project manager do wrong?

A. The project manager should not have submitted the change request since the risk was unknown.

B. The project manager did not account for all possible risks during project planning.

C. The project manager should not have included the schedule baseline in the change request.

D. The project manager used contingency reserves instead of management reserves.

303. A project is six months into its nine-month projected duration, and the project manager is reporting that the project is at least three months behind schedule because certain key stakeholders were resistant to any changes that might occur as outcomes of the project. What might have been done differently during project planning to have avoided this situation?

A. Better execution of the Manage Stakeholder Engagement process

B. Development of a stakeholder engagement assessment matrix

C. Creation of a comprehensive stakeholder register

D. Establishment of a more robust communications management plan

304. A project manager for a software development project has collected the work performance data and used the requirements documentation and requirements traceability matrix to generate the work performance information regarding variances in the project work compared to the baseline. What process is the project manager performing?

A. Validate Scope

B. Control Scope

C. Manage Quality

D. Direct and Manage Project Work

305. A project manager is currently in the process of prioritizing individual project risks by assessing their detectability, proximity, and impact value. The project manager would like to create a graphical representation of these three dimensions. What is the best course of action?

A. Generate a RACI chart

B. Prepare a requirements traceability matrix

C. Develop a bubble chart

D. Create a probability and impact matrix

306. A project manager is leading an infrastructure development project and is just starting the process of prioritizing individual project risks for further analysis. A stakeholder has expressed concern that the existing information about individual project risks may not be accurate and reliable. What is the best course of action?

A. Perform the Identify Risks process again

B. Capture the concern in the stakeholder register

C. Perform a risk data quality assessment

D. Conduct a risk probability and impact assessment

307. A project manager is leading a project to build a new model of all-terrain vehicle (ATV). The initial plan called for the suspension parts to be painted. However, in response to an issue captured in the issue log, it has been recommended to use powder coating instead of paint for better corrosion resistance. As it pertains to the acquisition of resources, what should be done next?

A. Deny the recommendation as it represents gold plating

B. Follow the resource management plan

C. Purchase the powder coating equipment and supplies

D. Submit a change request

308. In a steering committee meeting for a project to build a new state-of-the-art communications device, the committee chair reprimands the project manager for not using the company's file sharing system as required by the organization. The project manager explains that the project team chose a newer tool for the project, as it was much better. What most likely caused this situation?

A. The project manager did not research the enterprise environmental factors

B. The project manager did not review the organizational process assets

C. The project team did not investigate communication tools

D. The project manager did nothing wrong

309. A project manager is meeting with Sally, the program manager, to review the decomposed deliverables for a new product. Sally reviews the work breakdown structure and requests it to be arranged in the order the work should be performed. Is Sally correct saying that the work breakdown structure should be ordered according to how the work will be performed?

A. Sally is wrong. Work is decomposed and sequenced in the Define Activities process.

B. Sally is correct. Since she has superiority, the WBS should be ordered the way she wants it to be done.

C. Sally is wrong. The chronological order of tasks is defined in the Sequence Activities process.

D. Sally is correct. When decomposing the work, the order of tasks must be considered.

310. You are a project manager for a new product development project that is in the planning stages. Your project team has just finished creating the activities list and is now in the process of identifying and documenting relationships among the project activities. While meeting with your project team, you notice that a series of activities can be done in parallel but must finish in a specific sequence. Your team is debating which type of activity sequencing method to use. What would you tell them?

A. Activities diagramming method

B. Precedence diagramming method

C. Project schedule network diagram

D. Critical path method

311. You and your team have compiled your project's activity list, determined how the activities should be performed and analyzed the schedule. You are preparing information for the project sponsor to highlight the identified activities that may create a delay in the overall project schedule. Which of the following would be most useful in this situation?

A. Activity attributes

B. Project network diagrams

C. Duration estimates

D. Project calendars

312. You are the project manager for the construction of a new thin-crust pizza vending machine. You take all the information gathered in the project management plan to date and begin to develop a project schedule. When you reach the activity labeled as 6.5.3, you are unsure if a refrigeration specialist is needed for the installation of the cooling mechanism for the pizza dough. What project document would you reference in order to get information on the resources required for installing the cooling mechanism?

A. Resource calendar

B. Resource management plan

C. Activity attributes

D. Procurement management plan

313. You are leading a project to design a high-efficiency solar cell. The materials that you are acquiring for this project include copper, silver, and silicon among others, and you have also ordered custom built manufacturing equipment. Additionally, you have secured permission from the landlord to install a solar array on the roof of the corporate office for testing, and reserved a conference room for daily stand-up meetings. What is the result of your efforts?

A. Resource histogram

B. Resource management plan

C. Resource assignment matrix

D. Physical resource assignments

314. A project to build a new water treatment plant is in the planning stage. The project manager is starting the project management process of Plan Risk Management. The project sponsor is risk averse, and this will affect the risk management plan. In preparing the risk management plan, the project manager is seeking a high-level understanding of the project description and boundaries, high-level requirements, and risks. Where is the best place for the project manager to find this information?

A. Probability and impact matrix

B. Risk breakdown structure (RBS)

C. Project charter

D. Statement of work (SOW)

315. As a project manager, you will need the assistance of other stakeholders in order to identify the risks associated with your project. You want to determine who are the individuals that might participate in the process of identifying risks to the project, as well as those who are available to act as risk owners. Where should you look?

A. Responsibility assignment matrix (RAM)

B. Project charter

C. Risk breakdown structure (RBS)

D. Stakeholder register

316. As part of project planning, you and your project team are developing a comprehensive list of individual project risks and sources of overall project risk. You want to analyze the validity of assumptions and constraints to determine which pose a risk to the project. Which technique will be the most helpful for you?

A. Perform Qualitative Risk Analysis

B. Perform Quantitative Risk Analysis

C. Cost-benefit analysis

D. Data analysis

317. John is the project manager for a large construction project. He has just completed a Monte Carlo analysis simulation when he learns from a team member that some of the cost estimates used in the simulation were incorrect. John is highly risk-averse and concerned about this issue, so he meets with his team to discuss options for how to move forward. Based on this information, which choice below best describes what the team would likely do with the results from the Monte Carlo analysis?

A. Use the results; the simulation data can still be of value because incorrect estimates are accounted for in the algorithm

B. Reject the results and use the triangular distribution technique instead

C. Use the results but set aside additional contingency reserves to address the project risks

D. Reject the results; the Monte Carlo results would be inaccurate and should not be used

318. Tom is a project manager for a large software project. During project risk planning, Tom and his team are trying to decide whether to invest $10 million to develop new software or to instead invest $5 million to upgrade the existing software. The team is uncertain how strong demand will be for their product and, therefore, must account for this uncertainty in their analysis. What would be the best tool for the project manager to use in this case?

A. Tornado diagram

B. Monte Carlo analysis

C. Influence diagram

D. Decision tree analysis

319. Wendy is a project manager for an IT data center installation in a country that recently established independence. The country is in a strategic location for fiber optic communications, but the political climate is highly unstable. In order to keep the data center in the country but avoid unnecessary influence from the political dynamics, Wendy has negotiated with the U.S. Department of State to establish the data center in the basement of the U.S. Consulate in the capital city. This is an example of:

A. Risk transfer

B. Risk avoidance

C. Risk mitigation

D. Risk acceptance

320. A team member has been tasked to send the request for proposal (RFP), source selection criteria, and procurement statement of work (SOW) to potential sellers. The documentation is stored digitally on the corporate computer network. Which folder from the project directory is most likely to include these documents?

A. Bid documents

B. Requirements documentation

C. Procurement documentation

D. Test and evaluation documents

321. As a project manager for a small university, you are currently in the process of selecting a vendor to develop a textbook and other training materials for a new course. Several vendors are interested in bidding on the contract. During a bidder conference, one of the prospective suppliers asks about ownership of the intellectual property that will be created from the project. Which project document should have this information at this stage of the project?

A. Seller proposals

B. Requirements documentation

C. Source selection criteria

D. Procurement contract

322. A project manager is currently managing a manufacturing process improvement project which will be completed in five phases. The project manager has prepared the following chart to review the status of the project. Based on the information provided, what is the earned value of the project?

A. $7,750

B. $9,000

C. $20,000

D. $8,000

323. During a project's review, an executive states the project manager failed to forecast future outcomes based on past results, review how other projects addressed the similar issues, and analyze alternative solutions to issues. What has the project manager most likely overlooked with his intuitive manner of running the project?

A. Using analytical techniques

B. Conducting document analysis

C. Performing alternatives analysis

D. Utilizing trend analysis

324. You are developing a project management plan for a project that is part of a program. You have just been informed that a new procedure has been added to the program management plan. The procedure requires that all changes that exceed $10,000 in cost have to be reviewed by the change control board (CCB). What should you do?

A. Nothing; the program management plan and the project management plan are not correlated.

B. Submit a change request to the CCB to add the new procedure to the project management plan

C. Add the new procedure to the project management plan

D. Add an addendum to the project charter to reflect

325. The project is nearing its end. The executives are anxious to assign the project manager to other projects. However, before moving on, the project manager has to deliver the final product to the customer. What should the project manager do first?

A. Reassign resources to other projects

B. Obtain stakeholder approval

C. Close the project

D. Present a list of quality concerns to the customer

326. A project team member runs an earned value analysis (EVA) report. There is an unexpected spike in actual costs over the last three weeks. The team member shows the report to the project manager and based on her analysis presents four possible reasons for the spike. Which reason is most probable?

A. Soaring steel prices have impacted the fixed price with economic price adjustments procurement contracts

B. There was a strike at the loading dock which delayed many needed steel shipments until today

C. Fewer employees are showing up for work the past two weeks causing a backlog of unfinished work

D. Much higher than expected quarterly bonuses were given to executives during that three week period

327. During the project's iterations, the daily standup meetings have been held at 9 AM every day. Three of the project team members have missed or been late to the last seven meetings because they are running tests in another building each of those days. These tests will most likely continue for the rest of the iteration. What is the project manager's best action?

A. Start the meeting once everyone is present

B. Cancel the meetings

C. Start the meeting at different times every day until a particular time gets full attendance

D. Move the meeting to a set time later in the day

328. The updated version of the product is to be at the customer's location by the end of the week, but the team realizes they will be unable to complete the deliverable by then. The project manager and the team have looked for solutions to resolve this issue but there is nothing to avert missing the deadline. The deployment team who is supposed to install the product at the customer site is under a lot of stress to meet their deadline and are going to be furious that the update will not be there at the end of the week. What is the project manager's best action?

A. Wait until the deadline hoping the team eventually makes it

B. Send the status report to the customer

C. Make the phone call to the customer to inform them of the delay

D. Cancel the installation at the customer site

329. A dashboard viewable by all project stakeholders displays various statuses using the industry standard of red, yellow, and green colors. Throughout project execution, to meet the needs of the project and some of the project stakeholders, the project manager has been adding more colors to reflect additional statuses. This situation has created confusion among some of the stakeholders over the status naming conventions and meanings. What should the project manager do?

A. Revert the status to an industry standard of red, yellow, green

B. Explain the meaning of the new statuses to the stakeholders

C. Remove statuses from the dashboard to avoid confusion

D. Add a simpler status for the stakeholders who are confused

330. A new project manager is brought on the project. She wants to understand the process by which this particular project formally accepts deliverables. Which of the following will she have to reference?

A. The scope management plan

B. The stakeholder management plan

C. The quality management plan

D. The requirements management plan

331. The project has reached a stage where work is being done in seven countries. Project team members need to know in which currency they are to report their cost data. Which of the following should they reference?

A. Cost baseline

B. Cost management plan

C. Cost estimates

D. Cost breakdown structure

332. The project has to produce 10,000 new parts. The inspection points and their frequency along production must be determined. The part specifications and inspection modes to be used also need to be decided. In which process are these project plans defined?

A. Plan Resource Management

B. Create WBS

C. Manage Stakeholder Engagement

D. Plan Quality Management

333. An international project is entering its final phase. Some work in this phase must be done in the foreign country. Unsure if company policy requires a full-time employee onsite for project work in that country, which project artifact should the project scheduler reference?

A. Team management plan

B. Stakeholder engagement plan

C. Stakeholder register

D. Resource breakdown structure

334. A project has been initiated to search a large area for debris from an explosion of a failed prototype. The project is now in planning, and there is a debate among the team members on the type and quantity of resources needed to complete this activity. What should the project manager do first?

A. Select any resource and quantity to complete the task by the due date

B. Request the team to vote and make a decision based on majority

C. Research various levels of resource capability and skills, types, and sizes

D. Utilize a PMIS to manage resource pools and allocate resources

335. Services are still being billed to the project even though no additional services are required or requested. What is the best option for the project manager to take?

A. Confirm that no more services are needed and the procurement agreements are closed

B. Close all agreements with all service providers engaged with the project

C. Forward the service bills to the project management office for further review and approval

D. Continue paying the bills until the project is formally closed to avoid claims

336. Managing the project team for an agile based project, the project manager takes a servant role and allows the team to be self-organizing. Why is this possible?

A. The team relies on the project manager's leadership and assignments.

B. The team is comprised of subject matter experts that have specific roles and skills.

C. The team is comprised of generalists and able to support each other fluidly.

D. The team is larger than one project manager can put in one meeting room.

337. The following Gantt chart displays the schedule for a software upgrade project. The system analysis was completed on August 12th, but the system design and development activities are still in process as of October 3rd. Once the product is developed, the project team will need to test and deploy it, which must be completed by October 17th. What is the cost variance as of October 3rd?

A. -$650

B. $3,750

C. $650

D. $3,100

338. The project manager is trying to get sign off for a series of marketing materials. The work is rejected by the stakeholders responsible for sign off because of incorrect use of marketing standards. What should the project manager do before sending materials to the stakeholders again?

A. Perform quality control checks before validating the scope

B. Validate the scope before performing quality control

C. Create a work breakdown structure before validating the scope

D. Validate scope before communicating the project status

339. The project is not getting the marketing team to update the content of the online magazine website as scheduled. The outdated content is causing confusion among readers. What can the project manager do to engage the marketing team and make the needed changes as soon as possible?

A. Force the marketing manager to make the changes immediately

B. Communicate the importance and urgency of the change

C. Assign any another project team member to perform the work

D. Complain to other managers about the lack of response time

340. Your company was recently awarded a software development project, and you have just completed the scope management plan. The sponsor reviews the plan and states that the client specified the use of Scrum, while the plan indicates a waterfall approach. Which component of the project management plan did you most likely overlook while developing the scope management plan?

A. Project life cycle description

B. Development approach

C. Requirements management plan

D. The contract with the client

341. A project manager is developing a cost management plan and needs to determine the best source of funding for a project that is dictated by a legal requirement. The cost of capital is estimated at 9.7% for non-dividend paying equity, 6.7% for debt, and 5.1% for self-funding. The NPV of the project is $500,000 with an opportunity cost of $750,000. What is the project manager's best course of action?

A. Fund the project with equity since there are no dividend obligations

B. Select the self-funding option since it provides the lowest cost of capital

C. Perform an alternatives analysis since there are multiple factors to consider

D. Recommend the termination of the project since another project has a higher NPV

342. You are in the process of developing an approximation of the monetary resources needed to complete project work for a large-scale multinational project which will take at least seven years to complete. Your previous projects have all been domestic with short timeframes. As part of the process you are currently performing, what might you need to do differently compared with your past projects?

A. Create a stakeholder engagement assessment matrix

B. Develop a more robust risk management plan

C. Consider additional enterprise environmental factors

D. Include additional organizational process assets

343. A project manager is in the process of creating the quality management plan for a product development project. Currently, the project manager needs to understand and then estimate the cost of quality for a particular process. What is the best course of action?

A. Develop a RACI chart

B. Create a fishbone diagram

C. Construct a RAM

D. Build a SIPOC model

344. As a project manager, you are developing a resource management plan for your software development project, and you need to find a way to document and communicate the detailed descriptions of the team members' roles and responsibilities. What tool will best meet your needs?

A. Role-responsibility-authority form

B. RACI chart

C. Resource breakdown structure

D. Hierarchical chart

345. An apartment building construction project is currently in the planning stage. The project manager has decided to use analogous estimating to create the resource requirements and resource breakdown structure. What should the project manager do first?

A. Create estimates for the team and physical resources at the activity level

B. Research the organizational process assets

C. Develop the algorithm which will be used to calculate resource quantities

D. Review the lessons learned register

346. You are conducting the source selection analysis for an office building renovation project. One project requirement involves setting up the WiFi system once the hardware has been installed. The value of this procurement is relatively small, and you have decided that a full selection process does not make sense. With three prospective vendors listed as pre-approved sellers, what is the best course of action?

A. Utilize a sole source for the procurement

B. Use a firm fixed price contract

C. Establish a qualifications only selection method

D. Conduct a bidder conference

347. A company has been awarded a software development project which requires the development team to work at the client's office. The client has assigned each developer a cubicle from which to perform their work. During a daily standup meeting, a developer states that the team members are too isolated and colocating the team in a war room would increase productivity and quality. What should the project manager do first?

A. Explain to the team that colocation would impede productivity due to the inevitable distractions

B. Explain to the team that a war room was not specified in the contract

C. Negotiate with the client to make a war room available to the team

D. Capture a description of the developer's concern in the issue log

348. You are assigned to a software development project, and you are conducting a product review with an important client. Although the deliverables were previously verified, the client detects a defect and rejects one of the deliverables. What should you do?

A. Submit a change request to fix the deliverable

B. Refund the customer for the value of the deliverable

C. Ask the project team to repair the defect

D. Begin the claims administration process

349. A key stakeholder has been resistant to the project's objectives, and the support of this stakeholder is vital to the success of the project. The project manager has employed various engagement strategies which have been ineffective and needs to determine the underlying reason that stakeholder engagement is not having the planned effect. What should the project manager do next?

A. Develop a stakeholder engagement assessment matrix

B. Conduct data analysis

C. Submit a change request to update the stakeholder engagement plan

D. Perform an alternatives analysis

350. The agile project team members are all working in an open office space arrangement. There are many conversations happening concurrently throughout the day. Which of the following is the best option for the project manager?

A. Schedule frequent team checkpoints and post project artifacts in a transparent fashion

B. Request team members to hold off their conversations until formal meeting times

C. Record the conversations and post them in a shared repository

D. Designate afternoons as quiet work times

351. The project requires frequent input from the senior management team. Some of the past projects succeeded to engage the team, however, most failed as senior management is notorious throughout the organization of responding slowly and not attending meetings. What is the best strategy for the stakeholder engagement plan of the current project?

A. Patiently wait until management indicates that they are available to provide their input

B. Schedule regular, short update meetings at a constant time and convenient location

C. Review lessons learned from other projects involving the management stakeholders

D. Require one senior management representative to attend meetings or the project will be halted

352. Not all team members are properly checking out resources used in the project. What is the best option for the project manager?

A. Wait until there is a need or the team is impacted

B. Direct noncompliant team members to read the project management plan

C. Discuss the checkout rationale with the team

D. Remove the obstacle of checking out resources

353. Your sponsor has committed to building a high-speed rail from one major inland city, Azules, to the coast. You have two possible routes, either Brazos or Corazon. Given each route's costs, odds, and rewards of high demand and low demand in this decision tree, how would you quantify the expected monetary value of the route to Brazos?

A. 1.6 billion

B. -2 billion

C. 0.8 billion

D. 10.8 billion

354. Stakeholders are not sure what to do about the multiple failures the project has been experiencing recently. Changes need to be made quickly otherwise the project may be terminated as consistently missing its objectives. What should the project manager do first?

A. Recommend terminating the project as its objectives cannot be met

B. Consult with the project sponsor due to the urgency and the severity of the situation

C. Implement the most promising change immediately and transparently

D. Facilitate a discussion amongst the stakeholders on what should be changed

355. In a pharmaceutical project, human trials are to start soon. The CEO is thrilled about the success of the trials up to this point. She announces that the size of the patient pool for the trials should double from the one originally planned and results tracked in the new system launching this week. What should the project manager do first?

A. Ramp up production to match the demand of the CEO

B. Consider what might be included in a change request

C. Adjust the scope baseline to reflect the increased trial size

D. Communicate the change of direction with the stakeholders

356. The product trade show is approaching. The project team must produce functional prototypes for the event. The team is also tasked with many other competing project tasks. What can the project manager do in the next iteration planning?

A. Remove the other competing tasks from the schedule

B. Reprioritize the remaining work in the product backlog

C. Crash the project schedule by adding more resources

D. Move the prototype work to be on the critical path

357. The project sponsor is concerned about possible ethics violations between the project and vendors. What independent review can the sponsor order?

A. Team assessment

B. Performance review

C. Monte-Carlo analysis

D. Procurement audit

358. The project manager and the team decide that the project will be divided into five-week iterations with two weeks in between for retrospectives and iteration planning. Where is this documented?

A. Schedule management plan

B. Agile Practice Guide

C. Schedule network diagrams

D. Project charter

359. Sharing of project information is of utmost importance to the organization. Project knowledge is shared on multiple systems, services, and apps. The array of locations is becoming overwhelming for some of the project team members. What is the best option for the project manager to manage the project knowledge in this situation?

A. Close down some of the systems that the project team notes as burdensome

B. Consolidate or streamline sharing processes where possible

C. Compromise with the team to allow each to post in the tool they find most productive

D. Coordinate a weekly meeting to post all the team's knowledge at once

360. All the following occur during the planning process group EXCEPT:

A. Develop Project Charter

B. Create WBS

C. Estimate Costs

D. Sequence Activities

361. Your stakeholder register is your primary output and should at least contain:

A. Job descriptions, identification information, and stakeholder classification

B. Assessment information, scope information, and stakeholder classification

C. Assessment information, identification information, and stakeholder classification

D. Assessment information, identification information, and risk classification

362. Which one is not the causes of scope creep?

A. Poorly defined objectives

B. Lack of defined change control process

C. Changing stakeholder perspectives

D. Increased understanding of what is takes to get it done

E. Ability to say "NO"

363. A project is plagued by requested changes to the project charter. Who has the primary responsibility to decide if these changes are necessary?

A. The project manager

B. The project team

C. The sponsor

D. The stakeholders

364. Which project management process group generally takes the most project time and resources?

A. Initiating

B. Planning

C. Executing

D. Monitoring and controlling

E. Closing

365. True or False Conflict management is the process by which the project manager uses appropriate managerial techniques to deal with the inevitable disagreements that develop among those working toward project accomplishment.

A False

B. True

366. True or False. Each group of persons involved in the project should be assigned, and always needs to know their role and responsibility

A True

B. False

367. Project scope differs from product scope in that

A. Project scope is the work that needs to be accomplished to deliver a product, service, or result.

B. Project scope completion is measured against the features, functions, and product requirements.

C. Product scope completion is measured against the project management plan including all subsidiary plans.

D. Product scope is the work that needs to be accomplished to complete a project

368. An estimate created by looking at a similar project or activity and then adding or subtracting to or from the estimate based on the differences between the two is called

A. Parametric estimating

B. Analogous estimating

C. Bottom-up estimating

D. Exact estimating

369. All of the following are inputs to estimating activity durations except

A. Enterprise Environmental Factors & Organizational Process Assets

B. Risk Register & Scope Statement

C. Project Documents Updates & Requirements Specifications

D. Resource Calendars & Resource Breakdown Structure

370. Your project had a team of which consists of yourself, a tester, five developers and a communicator. As the project is behind schedule so one more developer has been assigned to your team. How many communication channels on your team now?

A 8

B. 9

C. 28

D. 36

371. True or False: In the context of a project, change is always a bad thing

A. True

B. False

371. True or False: The Backward Pass is used through the activities to determine the total duration of the project.

A. True

B. False

372. Lateral communication is NOT communication to from

A. Your customers.

B. Your friends.

C. Your subordinates

D. Your peers

373. You are assigned as the project manager in the middle of the project. The project is within the baselines, but the customer is not happy with the performance of the project. What is the first thing you should do?

A. Discuss it with the project team

B. Recalculate baselines

C. Renegotiate the contract

D. Meet with the customer

374. In our lessons the acronym RAM stands for

A. Responsibility Accountability Matrix

B. Responsibility Assignment Matrix

C. Resource Acquisition Management

D. Resource Aligned Management

E. Responsible Accountable Manageable

375. True or False: Influence means you have the right to apply resources, make decisions and give approvals.

A. False

B. True

376. What description defines Bottoms Up Estimating?

A. A technique that analyzes activities on past projects and using them as a basis for estimating costs.

B. A technique that uses a mathematical model to estimate costs.

C. A technique that involves estimating the cost of individual work packages or individual schedule activities with the lowest level of detail.

377. In Earned Value Management Technique, you can compute the Estimate To Completion (ETC) by applying which of following formula? (Notes: EAC: Estimate At Completion)

A. ETC = EAC-AC

B. ETC = EAC + AC

C. ETC EAC AC

D. ETC EAC/AC

378. True or False Your role as the project manager during quality control is to implement the quality management plan using the appropriate tools and techniques, in order to ensure that work is being performed according to required quality standards.

A False

B. True

379. Which of the following action should not include in the Scope Management Plan?

A. Prepare a project scope statement based upon the project charter.

B. Enable the creation and maintenance of the project work breakdown structure (WBS)

C. Define how format verification and acceptance of the completed project deliverables will be accomplished.

D. Control how requests for changes to the project scope will be processed.

E. Define how to identify and manage triple constraints

380. You have finished planning and have begun executing the project when the client asks if you would shorten the project duration so that the project can finish 2 weeks earlier than the original plan. How are the triple constraints affected?

A. Scope and cost may both be affected

B. Neither scope nor cost will be affected in any situation

C. Cost will reduce as the project duration is shortened and scope is not changed

D. There is no relevant option except the project must be cut down on scope

381. Which one is NOT the approach to shorten your project schedule?

A. Fast Tracking

B. Crashing

C. Reducing

382. Which element should NOT be included in risk management plan?

A. Budgeting

B. Timing

C. Roles and Responsibilities

D. Risk Register

383. Which organization structure can provide the most power for the project manager?

A. Functional

B. Weak Matrix

C. Balanced Matrix

D. Strongest Matrix

E. Projectized

F. Medium Matrix

384. Which of the components below do you think NOT belong in the cost management plan?

A Units of measure

B. Eamed value rules

C. Control thresholds

D. RACI matrix

385. A market demand, a business need, and a legal requirement are examples of

A. Reasons to hire a project manager

B. Reasons projects are initiated

C. Reasons people or businesses become stakeholders

D. Reasons to sponsor a project

386. True or False Project quality focuses on the project management processes used to meet project objectives.

A. False

B. True

387. The definition of a stakeholder includes:

A. People and organizations that are not impacted by your project.

B. Organizations impacted by your project but not people, they are all part of the impacted organizations.

C. The people or organizations that are positively or negatively impacted by your project.

D. People who are impacted by your project, but not organizations impacted by your project.

388. True or False: The danger of estimating using the same parametric model is the no longer applicable of historical data.

A. True

B. False

389. True or False: Project scope statement is better to define inclusions (in-scope items) than ide exclusions (out of scope items).

A. False

B. True

390. True or False: Using top-down estimating techniques when activity durations or resource quantities are uncertain.

A. True

B. False

391. True or False: The sender is responsible to provide feedback to acknowledge that the sent message has been received and understood. The receiver is responsible to make sure the sent message is clear, complete, and appropriate.

A. True

B. False

392. A company is making an effort to improve its project performance and create historical records of past projects. What is the best way to accomplish this?

A. Create project management plan

B. Create lessons learned

C. Create progress reports

D. Create status reports

393. All the following are characteristics of a project EXCEPT:

A. It is temporary

B. It has a definite beginning and end

C. It has interrelated activities

D. It repeats itself every month

394. Which of the following is NOT true regarding milestones?

A. Identify major events of the project deliverables

B. They are some points in time which have no duration

C. They are completely defined in the project charter

D. They are supported by activities on detail schedules

395. True or False: Performance reporting aims to inform stakeholders how resources are being used to achieve the project's objectives.

A. True

B. False

396. During executing, the project manager determines that a change is needed to material purchased for the project. The project manager calls a meeting of the team to plan how to make the changes. This is an example of

A. Management by objectives

B. Lack of a change management plan

C. Good team relations

D. Lack of a clear work breakdown structure

397. Effective project integration usually requires an emphasis on:

A. The careers of the team members

B. Timely updates to the project management plan

C. Effective communication at key interface points

D. Product control

398. Which of the following is included in a project charter?

A. A risk management strategy

B. Work package estimates

C. Detailed resources estimates

D. The business case for the project

399. You and another project manager disagree over whether a team member should work on your team or on her team. You decide that the team member can work for the other project manager and suppose that the other project manager will support you in the future. The truth is you wanted this person working on your project.

The conflict resolution approach you have used is:

A. Compromising

B. Smoothing

C. Confronting

D. Forcing

400. To calculate early start (ES) of an activity which has only one predecessor, you will

A. Take the early finish of its immediate predecessor.

B. Take the early start of its immediate predecessor.

C. Take the late finish of its immediate predecessor.

D. Take the late start of its immediate predecessor.

401. A project manager may use each of their work packages.

to make sure the team members clearly know what is included in

A. The project scope statement

B. The product scope

C. The WBS dictionary

D. The WBS

402. Your Schedule Performance Index (SPI) is greater than 1 means you are:

A. on schedule.

B. behind schedule.

C. ahead of schedule.

403. When you schedule work in a specific order because it cannot be completed any other way, what is the type of dependency used?

A. Discretionary

B. Internal

C. Mandatory

D. External

404. One of the stakeholders of the project contacts the project manager to discuss some additional scope they would like to add to the project. The project manager asks for details in writing and then works through the Control Scope process. What should the project manager do next when the evaluation of the requested scope is complete?

A. Ask the stakeholder if any more changes are expected

B. Complete integrated change control

C. Make sure the impact of the change is understood by the stakeholder

D. Find out the root cause of why the scope was not identified during project planning

405. True or False: Your role as the project manager during quality control is to work with a representative of quality control department who will create a test plan and test cases which will be used to test the product you are creating in order to prevent defects from reaching your customer.

A. False

B. True

406. True or False: Your role as the project manager during quality assurance manager who will create a test plan and test cases which will be used to test the product you are creating in order to prevent defects from reaching your customer

A. False

B. True

407. True or False: Your role as the project manager during quality control is to implement the quality management plan using the appropriate tools and techniques, in order to ensure that work is being performed according to required quality standards.

A. True

B. False

408. True or False: Project scope statement is better to define inclusions (in-scope items) than identify only exclusions (out of scope items).

A. False

B. True

409. Which one of these should be the view of conflict?

A. Caused by troublemakers

B. Often beneficial

C. Should be avoided

D. Must be suppressed

410. True or False: Quality management is the job done by project manager himself/herself to determine quality policies, objectives, and responsibilities so that the project will satisfy the needs for which it was undertaken.

A. False

B. True

411. Which of the following is true about the development of a project charter?

A. The sponsor creates the project charter, and the project manager approves it

B. The project team creates the project charter, and the PMO (Project Management Office) approves it

C. The executive manager creates the project charter, and the functional manager approves it

D. The project manager creates the project charter, and the sponsor approves it

412. You and your team have identified a risk that is a threat to your ability to successfully meet project objectives. The risk involves team members from your company performing work which requires training, certification, and many hours of experience. You have one newly certified team member and others who are still in training. Which do you think is your best response to this risk?

A. Acknowledge your lack of expertise and set aside some contingency reserve to cover the risk.

B. Change the scope of the project so that this type of work is excluded and introduce a new risk, that of an unhappy sponsor.

C. Let the team do the work and see what happen, do not prepare any other response.

D. You have budget to hire external resources and there is a vendor you can hire who specialized in this type of work, hire them.

413. A past project took 20,000 hours to complete. Your new project is adding some additional scope and that scope is estimated to take 10,000 additional hours. There is some work that was completed in the previous project that will not be completed in this project. That work is estimated at 5,000 hours. Labor rates have increased 10%, the old rate was $25 per hour. Your estimate for the new project is $687,500. Which estimating method is used?

A. Parametric estimating

B. Analogous estimating

C. Bottom-up estimating

D. Three-point estimating

414. True or False: Your project might pay more in order to reduce the schedule when using Fast Tracking approach, but that is not often true if using Crashing approach.

A. True

B. False

415. During status review meetings to evaluate project performance and progress, which tool or technique is NOT preferred to use?

A. Variance analysis

B. Trend analysis

C. Earned Value Management (EVM)

D. Requirement analysis

416. All of the following tools and techniques can be valuable in risk identification, EXCEPT:

A. SWOT (Strengths, Opportunities, Weaknesses, Threats)

B. Reviewing and evaluating project documents

C. Reviewing similar projects executed in past

D. EVM (Earned Value Management)

417. An output of the Close Project or Close Phase process is the creation of:

A. Project archives

B. A project charter

C. A project management plan

D. A risk management plan

E. A communication plan

418. You are the project manager of the large project and you are requesting your team members to create the work breakdown structure. Some of team members are angry that you are asking them to do "extra work". Which of the following is the best thing you could tell the members to convince them to use work breakdown structure?

A. Work breakdown structure will prevent work from slipping through the cracks

B. Work breakdown structure is of greater value on large project

C. Work breakdown structure is best when the project involves contracts

D. Work breakdown structure is the only way to identify risks

419. In a matrix-based organization:

A. Team members are always assigned to the project full time.

B. A project manager is not assigned to the team.

C. The project manager acts as manager of the team.

D. The functional manager has stronger power than the project manager's power.

E. The power of project manager and the power of managers of teams are depending on the organization's specific matrix type

420. True or False: Risk management is one-time process. You need to plan for all possible risks at the project beginning and then follow defined actions to control those risks until they are closed or cancelled.

A. False

B. True

421. Which of the following best describes a project management plan?

A. A printout from project management software

B. A bar chart

C. Scope, risk, resource, and other management plan

D. A project schedule

422. Which one is the correct matching of communication methods and the explanations?

Communication methods:

(1) Interactive

(2) Push

(3) Pull

Explanations:

(a) Between two or more parties and multidirectional; the most efficient way to ensure common understanding.

(b) Sent to recipients; does not ensure it was actually received and understood.

(c) Recipients must access the information; works for large amounts of information or large audiences, each

recipient accesses at their own discretion.

A. (1)&(a), (2)&(b), (3)&(c)

B. (1)&(a), (2)&(c), (3)&(b)

C. (1)&(b), (2)&(c), (3)&(a)

D. (1)&(b), (2)&(a), (3)&(c)

E. (1)&(c), (2)&(a), (3)&(b)

F. (1)&(c), (2)&(b), (3)&(a)

423. Which one of these most correctly defines contingency reserve?

A. Per our lesson, management reserve and contingency are exactly the same.

B. Contingency reserve is not tied to any specific work packages nor activities.

C. Contingency reserve is tied to specific work packages or activities.

D. Contingency reserve is tied to only one specific milestone.

424. A project manager has little project experience, but she has been assigned as the project manager of a new project. Because she will be working in a matrix organization to complete her project, she can expect communications to be

A. Simple

B. Open and accurate

C. Complex

D. Hard to automate

425. Which of the following is NOT the output of Plan Scope Management process? (Choose 2 answers)

A. Scope Management Plan

B. Requirement Management Plan

C. Time Management Plan

D. Cost Management Plan

426. A cost can be either variable or fixed. Which of the following statements are correct (choose 2 answers)?

A. Variable costs: These costs change with the amount of production. Examples include the cost of material, supplies, and wages.

B. Fixed costs: These costs do not change as production changes. Examples include the cost of setup, rent, utilities, etc.

C. Fixed costs: These costs change with the amount of production. Examples include the cost of material, supplies, and wages.

D. Variable costs: These costs do not change as production changes. Examples include the cost of setup, rent, utilities, etc.

427. Given 14.000 USD is the most likely of the estimated cost of the activity, 8.000USD is the optimistic value and 26.000USD is the pessimistic one. By using the PERT (Program Evaluation and Review Technique) analysis to calculate the expected activity cost, which of the following is the result?

A. 16.000 USD

B. 12.000 USD

C. 15.000 USD

D. 21.000 USD

428. The network diagram can be used to:

A. Control the cost performance of the project

B. Show project schedule performance over time

C. Identify project resource requirements

D. Identify opportunities to compress the project schedule

E. Help to justify project quality metrics

429. Your stakeholder register should not contain:

A. Identification information

B. Assessment information

C. Stakeholder classification

D. Scope information

430. True or False: It should not to add extra cost to the estimates when you are concerned that your estimates might not be correct, especially if you think they are too low.

A. True

B. False

431. True or False: Your project might pay more in order to reduce the schedule when using Crashing approach, but that is not often true if using Fast Tracking approach.

A. True

B. False

432. The person who should be in control of the project during project planning is the

A. Project manager

B. Team member

C. Functional manager

D. Sponsor

433. A project manager has received some help from the team, and she needs help from them again so that she can create a detailed project budget. Which project management process group is she in?

A. Initiating

B. Planning

C. Executing

D. Monitoring and controlling

E. Closing

434. During a project team meeting, a team member suggests an enhancement to the scope that is beyond the scope of the project charter. The project manager points out that the team needs to concentrate on

completing all the work and only the work required. This is an example of

A. Change management

B. Scope management

C. Quality analysis

D. Scope decomposition

435. Which statement is not correct?

A. Project scope is the work that needs to be accomplished to deliver a product, service, or result.

B. Product scope completion is measured against the product requirement.

C. Project scope completion is measured against the project management plan and specially the project scope statement, the work breakdown structure (WBS), and the WBS dictionary.

D. Product scope is the work that needs to be accomplished to complete a project

436. We discussed four types of organization structures, they are:

A. Functional, Matrix-Based, Projectized and Composite

B. Weak, Medium, Strong and Projectized

C. Weak, Balanced, Strong and Projectized

D. Functional, Weak, Strong and Composite

437. Given Tm is the most likely of the estimated duration of the activity, To is the optimistic value and Tp is the pessimistic one. The PERT (Program Evaluation and Review Technique) analysis calculates the expected activity duration (Te) using which of the weighted average of these three estimates?

A. Te(Tm + 4*To + Tp)/6

B. Te (To+ 4*Tp + Tm)/6

C. Te (Tp+ 4*Tm + To)/6

D. Te (Tm + To + Tp)/3