- SP24

- Request: Your project team has completed a workload equivalent to $3,000 and has spent $4,000 to date. Assume that you were budgeted $5,000 for the work scheduled. At the start, the team estimated a project budget of $9,000 and that the project needed 12 months to finish. Calculate and give your calculations and comments on the project’s current status and the forecasts to complete the project in terms of cost and schedule.

Solution:

### 1. Given Data:

- EV (Earned Value) = $3,000 (work completed)

- AC (Actual Cost) = $4,000 (spent to date)

- PV (Planned Value) = $5,000 (budgeted for work scheduled)

- BAC (Budget at Completion) = $9,000 (total project budget)

- Planned Duration = 12 months

2. CPI & SPI

Cost Performance Index (CPI):

CPI = EV/AC = 3,000/4,000 = 0.75

→ A CPI of 0.75 (< 1) indicates the project is over budget. For every dollar spent, only $0.75 of value is earned.

Schedule Performance Index (SPI):

SPI = EV/PV = 3,000/5,000 = 0.6

→ An SPI of 0.6 (< 1) indicates the project is behind schedule. The team has completed less work than planned(40%).

### 3. Project’s Current Status

- Cost Status:

  - The project is over budget (CPI = 0.75). The team is spending more than planned on the work completed ($4,000 spent vs. $3,000 worth).

- Schedule Status:

  - The project is behind schedule (SPI = 0.6). The team has only completed $3,000 of the $5,000 worth of work planned at this point(40%).

#### 4. Cost Forecast:

To estimate the Estimate at Completion (EAC):

EAC = BAC/CPI = 9,000/0.75 = 12,000 ($)

→ The forecasted total cost to complete the project is $12,000, which exceeds the original budget of $9,000.

The Estimate to Complete (ETC) (remaining cost):

ETC = EAC − AC = 12,000 − 4,000 = 8,000 ($)

→ The team will need an additional $8,000 to complete the project.

#### 5.  Schedule Forecast:

To estimate the total project duration:

Estimated Total Duration = Planned Duration / SPI = 12/0.6 = 20 months

→ The project is forecasted to take 20 months to complete, compared to the original 12 months.

### 6. Comments on Project Status and Forecasts

- Current Status:

  - Cost: The project is significantly over budget (CPI = 0.75). The team is spending 33% more than the value of work completed, indicating inefficiencies or unanticipated costs.

  - Schedule: The project is well behind schedule (SPI = 0.6). The team has only accomplished 60% of the planned work, suggesting delays or slower progress than expected.

- Forecasts:

  - Cost: The project is projected to cost $12,000, a 33% overrun from the original $9,000 budget. The team needs an additional $8,000 to complete the remaining work.

  - Schedule: The project is expected to take 20 months to complete, 8 months longer than the original 12-month plan.

  - Implications: The low CPI and SPI suggest serious issues in cost control and productivity. Immediate corrective actions (e.g., optimizing resources, revising the schedule, or addressing bottlenecks) are needed to mitigate further overruns.

- SP24 - RE

- Request: Given the following information for a one-year project, after 2 months since the project started, answer the below questions:
 PV (Planned Value) = $22,000;
 EV (Earned Value) = $20,000;
 AC (Actual Cost) = $25,000;
 BAC (Budget At Completion) = $120,000

a) What are the cost and schedule performance of the project? Show your calculations.
b) How is the project doing in terms of project cost and time (schedule)? Explain those statuses.
c) Use the CPI to calculate the estimated rest cost the team would need to complete the project.
d) Use the SPI to estimate how many months it will take the team to finish this project.

Solution:

### Given Data:

- PV = $22,000

- EV = $20,000

- AC = $25,000

- BAC = $120,000

- Planned Duration = 12 months

- Time Elapsed = 2 months

### a) Cost and Schedule Performance

- Cost Performance Index (CPI):

CPI = EV/AC = 20,000/25,000 = 0.8

- Schedule Performance Index (SPI):

SPI = EV/PV = 20,000/22,000 = 0.909

### b) Project Cost and Schedule Status

Cost Status:

CPI = 0.8 (< 1) → Over budget. Spending $25,000 for $20,000 of work indicates cost inefficiencies.

Schedule Status:

SPI = 0.909 (< 1) → Behind schedule. Completed $20,000 of $22,000 planned, progressing at 90.9% of the planned rate.

### c) Estimated Rest Cost (ETC)

Estimate at Completion (EAC):

EAC = BAC/CPI = 120,000/0.8 = 150,000 ($)

Estimate to Complete (ETC):

ETC = EAC - AC = 150,000 - 25,000 = 125,000 ($)

→ The team needs $125,000 to complete the project.

### d) Estimated Time to Finish

Estimated Total Duration:

Estimated Duration = Planned Duration/SPI = 12/0.909 ≈ 13.2 months

Remaining Time:

Remaining Time = 13.2 - 2 = 11.2 months

→ Project will take ~13.2 months total, with ~11.2 months remaining.

- FA24

- Request: The project was expected to cost $6 million for three months. At the end of one month, you use earned value management as a performance management technique and get the following information:
   EV = $2.3 million; PV = $2.8 million; AC = $2.1 million

Calculate and give your comments (current status, forecast, and recommended adjustment) on the schedule and cost performance of the project.

Solution:

- Given Data:

- EV (Earned Value) = $2,300,000 (work completed)

- AC (Actual Cost) = $2,100,000 (spent to date)

- PV (Planned Value) = $2,800,000 (budgeted for work scheduled)

- BAC (Budget at Completion) = $6,000,000 (total project budget)

- Planned Duration = 3 months

- Time Elapsed = 1 month

- CPI & SPI:

Cost Performance Index (CPI):

CPI = EV/AC = 2,300,000/2,100,000 ≈ 1.095

→ A CPI of 1.095 (> 1) indicates the project is under budget. For every dollar spent, $1.095 of value is earned.

Schedule Performance Index (SPI):

SPI = EV/PV = 2,300,000/2,800,000 ≈ 0.821

→ An SPI of 0.821 (< 1) indicates the project is behind schedule. The team has completed less work than planned.

- Project’s Current Status:

- Cost Status: The project is under budget (CPI = 1.095). The team is spending less than planned on the work completed ($2,100,000 spent vs. $2,300,000 worth).

- Schedule Status: The project is behind schedule (SPI = 0.821). The team has only completed $2,300,000 of the $2,800,000 worth of work planned at this point.

- Cost Forecast:

To estimate the Estimate at Completion (EAC):

EAC = BAC/CPI = 6,000,000/1.095 ≈ 5,479,452 ($)

→ The forecasted total cost to complete the project is $5,479,452, which is under the original budget of $6,000,000.

The Estimate to Complete (ETC) (remaining cost):

ETC = EAC − AC = 5,479,452 − 2,100,000 ≈ 3,379,452 ($)

→ The team will need an additional $3,379,452 to complete the project.

- Schedule Forecast:

- To estimate the total project duration:

Estimated Total Duration = Planned Duration / SPI = 3/0.821 ≈ 3.65 months

→ The project is forecasted to take 3.65 months to complete, compared to the original 3 months.

- Remaining Time:

Remaining Time = 3.65 − 1 ≈ 2.65 months

→ Approximately 2.65 months remain to complete the project.

- Comments on Project Status and Forecasts:

- Current Status:

  - Cost: The project is under budget (CPI = 1.095). The team is spending 9.5% less than the value of work completed, indicating cost efficiency.

  - Schedule: The project is behind schedule (SPI = 0.821). The team has only accomplished 82.1% of the planned work, suggesting delays or slower progress than expected.

- Forecasts:

  - Cost: The project is projected to cost $5,479,452, an 8.7% savings from the original $6,000,000 budget. The team needs an additional $3,379,452 to complete the remaining work.

  - Schedule: The project is expected to take 3.65 months to complete, 0.65 months (~19.5 days) longer than the original 3-month plan. With 1 month elapsed, the team faces 2.65 months of work remaining. Implications: The high CPI is positive, but the low SPI indicates schedule issues. Immediate corrective actions (e.g., reallocating resources, addressing bottlenecks, or fast-tracking tasks) are needed to recover the schedule. Use cost savings to support recovery efforts if necessary while ensuring quality is maintained. Communicate status to stakeholders to align expectations.

- FA24 - RE

- Request: Assuming that your project was reported with the following status:

AC = $120,000, PV = $125,000, CV = -10,000 = EV - AC

Calculate and give your comments (current status, forecast, and recommended adjustment) on the schedule and cost performance of the project.

Solution:

- Given Data:

- AC (Actual Cost) = $120,000 (spent to date)

- PV (Planned Value) = $125,000 (budgeted for work scheduled)

- CV (Cost Variance) = -$10,000

- EV (Earned Value) = AC + CV = 120,000 - 10,000 = $110,000 (work completed)

- BAC (Budget at Completion) = Unknown Planned

- Duration = Unknown

- CPI & SPI:

Cost Performance Index (CPI):

CPI = EV/AC = 110,000/120,000 ≈ 0.917

→ A CPI of 0.917 (< 1) indicates the project is over budget. For every dollar spent, $0.917 of value is earned.

Schedule Performance Index (SPI):

SPI = EV/PV = 110,000/125,000 = 0.88

→ An SPI of 0.88 (< 1) indicates the project is behind schedule. The team has completed less work than planned.

- Project’s Current Status:

Cost Status: The project is over budget (CPI = 0.917). The team is spending more than planned on the work completed ($120,000 spent vs. $110,000 worth).

Schedule Status: The project is behind schedule (SPI = 0.88). The team has only completed $110,000 of the $125,000 worth of work planned at this point.

- Cost Forecast:

To estimate the Estimate at Completion (EAC):

EAC = BAC/CPI

→ BAC is unknown, so EAC cannot be calculated numerically. CPI < 1 suggests cost overrun.

The Estimate to Complete (ETC) (remaining cost):

ETC = (BAC - EV)/CPI

→ Without BAC, ETC cannot be calculated, but the trend indicates higher-than-planned remaining costs.

- Schedule Forecast:

To estimate the total project duration:

Estimated Total Duration = Planned Duration / SPI

→ Planned Duration is unknown, so duration cannot be calculated. SPI = 0.88 suggests the project will take ~1.136 times the planned duration.

Remaining Time:

→ Cannot be calculated without planned duration and time elapsed.

- Comments on Project Status and Forecasts:

- Current Status:

  - Cost: The project is over budget (CPI = 0.917). The team is spending 9.1% more than the value of work completed, indicating inefficiencies or unanticipated costs.

  - Schedule: The project is behind schedule (SPI = 0.88). The team has only accomplished 88% of the planned work, suggesting delays or slower progress than expected.

- Forecasts:

  - Cost: Without BAC, the exact overrun is unknown, but CPI < 1 indicates the final cost will exceed the budget.

  - Schedule: Without planned duration, the exact delay is unknown, but SPI = 0.88 suggests ~13.6% longer than planned.

- Implications: Low CPI and SPI indicate cost and schedule issues. Immediate corrective actions (e.g., cost audits, resource reallocation, or addressing bottlenecks) are needed. Obtain BAC and planned duration for precise forecasts. Communicate with stakeholders to manage expectations and plan recovery.