1. Lý thuyết liên quan

- Project Life Cycle (Vòng đời dự án): là tập hợp các phase (giai đoạn) liên tiếp, từ khi dự án được khởi tạo đến khi chính thức kết thúc. Theo PMBOK thường gồm:

  - Initiation

  - Planning

  - Execution

  - Monitoring & Controlling

  - Closing

- Phase: mỗi phase là một nhóm công việc để tạo ra một hoặc nhiều deliverable (sản phẩm bàn giao) cụ thể.

- Deliverable: kết quả đầu ra có thể đo đếm, kiểm chứng được (sản phẩm, tài liệu, báo cáo…), dùng để chứng minh giai đoạn đó đã hoàn thành.

- Iteration (trong Agile): một chu kỳ phát triển ngắn (ví dụ Sprint), lặp đi lặp lại, mỗi iteration cũng phải bàn giao một increment (tăng trưởng sản phẩm) có giá trị.

- Project Charter: tài liệu khởi tạo dự án, xác định mục tiêu, phạm vi sơ bộ, stakeholders chính.

- Stakeholder Register: danh sách và phân tích các bên liên quan (stakeholders).

- Work Breakdown Structure (WBS): cấu trúc phân chia công việc, tách nhỏ scope thành các phần dễ quản lý.

- Project Management Plan: tài liệu tổng hợp các kế hoạch con (scope management plan, schedule management plan, cost management plan, risk management plan…).

- Baseline: kế hoạch gốc (scope baseline, schedule baseline, cost baseline) dùng để so sánh với kết quả thực tế.

- Risk Register: nhật ký rủi ro, liệt kê các rủi ro, đánh giá xác suất – tác động, phương án ứng phó.

  - Mục đích: làm “bản đồ đường” chi tiết cho toàn bộ dự án, đảm bảo mọi khía cạnh được hoạch định trước.

- Work Breakdown Structure (WBS)

  - Nội dung: sơ đồ phân chia công việc thành các work package, cấp độ 1 – 2 – …

  - Mục đích: giúp phân bổ resources, ước tính thời gian – chi phí và theo dõi tiến độ dễ dàng.

Here’s your sample answer fully in English, followed by a quick review of your own version:

Exercise 3: (SU24-RT)
 Identify at least 4 project phases/iterations and 2 main deliverables in each phase/iteration. You need to provide the description for each of the identified deliverables about its content/purpose.

## Sample Solution

Based on an Agile approach, the LMS project is organized into four iterations.

### Iteration 1: Foundation Setup (Weeks 1–2)

Purpose: Lay the groundwork by defining scope, setting up the environment, and designing the high-level architecture.

- Product Backlog

  - Description: A comprehensive list of all user stories, features, and tasks required for the LMS.

  - Purpose: Serves as the development roadmap and helps the team prioritize work for upcoming sprints.

- System Architecture Document

  - Description: A high-level design that illustrates system components, their interactions, data flows, and the chosen technology stack.

  - Purpose: Provides developers with a clear blueprint to build a scalable and maintainable LMS.

### Iteration 2: Core Functionality Development (Weeks 3–6)

Purpose: Build the essential features that enable basic LMS operations.

- User Account Management Module

  - Description: Functionality for user registration, authentication (login/logout), role assignment (admin, instructor, learner), and profile maintenance.

  - Purpose: Ensures secure access control and personalized experiences for different user types.

- Course Creation Tools

  - Description: Interfaces and APIs allowing instructors to create, edit, and organize course content, including lessons, quizzes, and multimedia assets.

  - Purpose: Empowers instructors to author and manage educational content independently.

### Iteration 3: User Interaction Features (Weeks 7–10)

Purpose: Enhance usability and gather early feedback on learner-facing functionality.

- Course Browsing & Enrollment Interface

  - Description: A polished front-end allowing learners to search, filter, preview, and enroll in courses.

  - Purpose: Streamlines course discovery and simplifies the enrollment workflow.

- Test Report & Feedback Integration

  - Description: Results of functional, usability, and performance tests, plus a log of stakeholder feedback with planned adjustments.

  - Purpose: Validates system stability and aligns the product more closely with user needs.

### Iteration 4: Deployment & Launch (Weeks 11–12)

Purpose: Finalize, validate with end users, and roll the LMS out to production.

- Deployed LMS Platform

  - Description: A live, fully configured LMS instance on staging/production servers, with core and advanced features enabled.

  - Purpose: Allows real users to start interacting with the system in its target environment.

- Training Materials & User Guides

  - Description: Documentation, video tutorials, and quick-start guides for administrators, instructors, and learners.

  - Purpose: Facilitates smooth onboarding and ensures stakeholders know how to use all LMS features effectively.