Changes

Link bài đọc tham khảo

1. Kiến thức liên quan

- Change Request: Yêu cầu thay đổi chính thức được tạo ra khi có sự khác biệt so với project baseline (scope, schedule, cost, chất lượng).

- Change Control Process: Quy trình quản lý thay đổi gồm các bước:

  - Identify: Ghi nhận và mô tả change request (mã số, người đề xuất, lý do).

  - Log: Ghi vào Change Log (trạng thái, ngày nộp, người chịu trách nhiệm).

  - Evaluate / Impact Analysis: Phân tích ảnh hưởng lên scope, timeline, budget, resources, chất lượng và rủi ro.

  - Review & Approve: Đưa vào Change Control Board (CCB) hoặc stakeholder để phê duyệt hoặc từ chối.

  - Implement: Thực hiện thay đổi nếu được phê duyệt, cập nhật project management plan và baseline.

  - Close: Đóng hồ sơ yêu cầu sau khi hoàn tất và báo cáo kết quả.

- Các loại thay đổi thường gặp:

  - Scope Change: Thêm, bớt hoặc điều chỉnh tính năng / deliverable.

  - Schedule Change: Đổi deadline, điều chỉnh milestone.

  - Cost Change: Tăng hoặc giảm ngân sách, phát sinh chi phí mới.

  - Resource Change: Thay đổi nhân sự, thiết bị hoặc bên cung cấp.

  - Quality Change: Thay đổi tiêu chuẩn chất lượng hoặc criteria nghiệm thu.

- Công cụ hỗ trợ quản lý thay đổi:

  - Change Log (Excel, hệ thống PMIS)

  - Impact Analysis Template

  - Configuration Management System (giúp theo dõi các phiên bản deliverable và baseline)

2. Mẫu trả lời (Tiếng Anh)

Documented Change Requests for the XYZ Corp Website Redesign Project

1. Addition of Multi-language Support

- Description: Introduce Vietnamese and Thai language options alongside English.

- Rationale: Expand market reach to Southeast Asia.

- Impact:

  - Scope: +2 new language modules, translation workflows

  - Schedule: +3 weeks for translation and testing

  - Cost: +$12,000 for localization services and QA

  - Resources: Hire 2 freelance translators and 1 localization tester

2. Integration with CRM System

- Description: Connect website user data to Salesforce CRM.

- Rationale: Streamline lead capture and customer follow-up.

- Impact:

  - Scope: Develop and test REST API connectors

  - Schedule: +2 sprints (4 weeks) for development and UAT

  - Cost: +$8,000 for API licensing and development

  - Quality: Additional security review and penetration testing

3. Mobile App Prototype for iOS/Android

- Description: Develop a basic mobile app prototype mirroring new website features.

- Rationale: Validate mobile UX before full investment.

- Impact:

  - Scope: Create clickable prototypes in Figma + review sessions

  - Schedule: +2 weeks for design and prototype testing

  - Cost: +$5,000 for UX designer and prototype tools

  - Risk: May divert resources from website development

4. Enhanced Accessibility Compliance (WCAG 2.1 AA)

- Description: Upgrade design and code to meet WCAG 2.1 AA standards.

- Rationale: Ensure legal compliance and improve usability for all users.

- Impact:

  - Scope: Audit current pages, implement ARIA labels, color contrast fixes

  - Schedule: +1 sprint (2 weeks) for audit and remediation

  - Cost: +$4,000 for accessibility audit tool and developer time

  - Quality: Higher QA effort; potential rework of existing components

5. Revised Content Strategy: Blog & Knowledge Base

- Description: Add a CMS-driven blog and FAQ/knowledge-base section.

- Rationale: Boost SEO, provide self-service support.

- Impact:

  - Scope: CMS setup, template design, initial content creation

  - Schedule: +3 weeks for CMS deployment and content writing

  - Cost: +$7,500 for copywriting and CMS licensing

  - Resources: Engage a content strategist and copywriter

Summary:
 Each proposed change follows the standard change control process: logged in the Change Log, analyzed for impact on baseline, reviewed by the CCB, and implemented only upon formal approval. This systematic approach ensures balanced trade-offs between business value and project constraints.