# Request 1 (20%): Stakeholder Identification & Management Strategies

- Project Sponsor (Executive Sponsor / CEO)

  - Influence: High – controls budget, scope approvals, and strategic alignment.

  - Interest: High – wants platform launched on time and within budget to drive growth.

  - Management Strategy:
 - Hold bi‑weekly steering committee meetings.
 - Provide concise executive summaries with RAG status.
 - Escalate major decisions promptly.

- Small‑Business Owners (End Users / Customers)

  - Influence: Medium – their adoption and feedback will determine platform success.

  - Interest: High – need an easy‑to‑use, cost‑effective store solution.

  - Management Strategy:
 - Run focus groups and usability testing sessions.
 - Maintain an open “customer advisory” Slack channel.
 - Incorporate feedback via prioritized user stories.

- Payment Gateway Providers

  - Influence: Medium – control integration ease, uptime, and transaction fees.

  - Interest: Medium – want reliable integration and transactional volume.

  - Management Strategy:
 - Establish clear API requirements and SLAs in a contract.
 - Schedule regular technical checkpoints during integration.
 - Maintain a “fallback” plan with a secondary provider.

- Development Team (In‑house Dev & External Contractors)

  - Influence: High – responsible for delivering features and quality.

  - Interest: High – I want clear requirements, a stable scope, and a manageable workload.

  - Management Strategy:
 - Adopt Agile cadence: daily stand‑ups, sprint planning, retrospectives.
 - Use a shared backlog with transparent prioritization.
 - Provide timely answers to blockers via a dedicated Slack channel.

# Request 2 (20%): Key Risks, Evaluation & Mitigation

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| 1. Payment‑integration failure | Medium (40%) | High (9/10) | • Implement and test with two gateway providers (Primary + Backup)• Automate failover logic in checkout flow |
| 2. Security breach/data leak | Low (20%) | Very High (10/10) | • Perform third‑party security audit and penetration tests• Enforce HTTPS, end‑to‑end encryption, WAF and regular patching |
| 3. Scope creep | High (60%) | Medium (6/10) | • Strict change‑control board (CCB) reviews all scope changes• Prioritize via MoSCoW and adjust schedule/budget for new requests |
| 4. Vendor onboarding delays | Medium (50%) | Medium‑High (7/10) | • Create a clear “Vendor Onboarding Kit” with checklists and sample data• Assign a dedicated vendor liaison coordinator• Use proactive reminders and escalation when deadlines slip |

# Request 3 (35%): Network Paths, Duration, Flexibility & Acceleration

a. All paths from Start → End
 1. Start → A → D → E → End   (4 + 8 + 5 = 17 days)
 2. Start → A → D → G → End   (4 + 8 + 3 = 15 days)
 3. Start → B → F → G → End   (2 + 7 + 3 = 12 days)
 4. Start → C → H → I → End   (3 + 8 + 3 = 14 days)

b. Minimum duration (Critical Path)

- The longest path is Start → A → D → E → End at 17 days.

c. Activities with the most total float (flexibility)

- B and F each have 5 days of total float (highest slack).

- Next: C, H, I each 3 days; G has 2 days.

d. Four schedule‑recovery solutions (recover 3‑day delay on Day 5 in D)

- Crashing Activity D
 - Add two additional developers to D to finish in 6 days (instead of 8).
 - Assumption: Resources will be onboarded immediately; marginal cost increase is acceptable.

- Fast‑tracking D → E Overlap
 - Begin E work on the portions of D that are complete after Day 6.
 - Assumption: E’s tasks are sufficiently independent of final D deliverables.

- Outsource Sub‐tasks of D
 - Contract a specialist vendor for non‑core subcomponents of D, reducing D by 2 days.
 - Assumption: vendor can mobilize within 2 days and maintain quality.

- Introduce Overtime & Double Shifts
 - Run two shifts on D for the next 3 days, accelerating by ~1 day each.
 - Assumption: the team is willing to work overtime; the overtime cost is budgeted.

# Request 4 (25%): Đánh giá hiện trạng & dự báo chi phí

Áp dụng Earned Value Management cho tình huống:

- EV = $300,000

- PV = $500,000

- AC = $400,000

- Cost Variance (CV) = EV – AC = $300k – $400k = –$100k ⇒ dự án over budget.

- Schedule Variance (SV) = EV – PV = $300k – $500k = –$200k ⇒ dự án behind schedule.

- Cost Performance Index (CPI) = EV / AC = 0.75 (< 1) ⇒ hiệu suất chi phí kém.

- Schedule Performance Index (SPI) = EV / PV = 0.6 (< 1) ⇒ hiệu suất tiến độ kém.

Dự báo chi phí (EAC, ETC)

- Theo hiệu suất hiện tại:

  - EAC = BAC / CPI = $800k / 0.75 ≈ $1,066,667

  - ETC = EAC – AC ≈ $1,066,667 – $400,000 = $666,667

Dự báo tiến độ

- Dự án ban đầu cần 6 tháng; PV tương ứng 62.5% ⇒ đã trôi qua 0.625×6 = 3.75 tháng.

- Remaining Planned Duration = 6 – 3.75 = 2.25 tháng.

- Forecast Remaining Duration = 2.25 / SPI = 2.25 / 0.6 = 3.75 tháng.

- Tổng dự báo thời gian hoàn thành = 3.75 (đã qua) + 3.75 (còn lại) = 7.5 tháng.

Kết luận:

- Dự án dự kiến hoàn thành trong 7.5 tháng, trễ 1.5 tháng so với kế hoạch ban đầu.

- Tổng EAC ~$1.067 triệu, vượt so với BAC $800k.